## Template
Improvement ID | Date Raised | Raised By | Source of Improvement | Source Reference | COBIT 2019 Objective | Governance/Management Area | Related Policy/Process/Control | Current Issue or Gap | Root Cause | Improvement Action | Expected Outcome | Risk or Opportunity Addressed | Priority | Impact | Effort | Action Owner | Accountable Executive | Target Start Date | Target Completion Date | Actual Start Date | Actual Completion Date | Status | RAG | Progress Commentary | Dependencies | Resources Required | Success Measure/KPI | Baseline Value | Target Value | Post-Implementation Result | Evidence Location | Validation Method | Validator | Validation Date | Closure Decision | Closure Approval By | Closure Approval Date | Lessons Learned | Next Review Date
[EXAMPLE: CI-2026-001] | [EXAMPLE: 2026-01-15] | [EXAMPLE: Internal Audit] | [EXAMPLE: Internal Audit] | [EXAMPLE: IA-2026-ITG-03] | [EXAMPLE: MEA02] | [EXAMPLE: Internal control monitoring] | [EXAMPLE: IT Control Self-Assessment Procedure] | [EXAMPLE: Control testing evidence is not consistently retained for quarterly IT governance controls.] | [EXAMPLE: Evidence retention requirements are not defined in the procedure.] | [EXAMPLE: Update the control self-assessment procedure to define mandatory evidence types, retention location, and review responsibilities.] | [EXAMPLE: Control evidence is complete, consistently retained, and available for assurance review.] | [EXAMPLE: Reduced risk of ineffective control monitoring and failed audit evidence requests.] | [EXAMPLE: High] | [EXAMPLE: High] | [EXAMPLE: Medium] | [EXAMPLE: IT Governance Manager] | [EXAMPLE: CIO] | [EXAMPLE: 2026-02-01] | [EXAMPLE: 2026-03-31] | [EXAMPLE: 2026-02-03] | [EXAMPLE: ] | [EXAMPLE: In Progress] | [EXAMPLE: Amber] | [EXAMPLE: Procedure update drafted; awaiting review by control owners.] | [EXAMPLE: Approval from IT Risk Committee] | [EXAMPLE: Process owner time and SharePoint repository update] | [EXAMPLE: Percentage of quarterly controls with complete evidence retained] | [EXAMPLE: 62%] | [EXAMPLE: 95%] | [EXAMPLE: ] | [EXAMPLE: SharePoint/ITGovernance/Controls/CSA/2026] | [EXAMPLE: Evidence review and sample testing] | [EXAMPLE: IT Risk Manager] | [EXAMPLE: ] | [EXAMPLE: Not Ready] | [EXAMPLE: ] | [EXAMPLE: ] | [EXAMPLE: ] | [EXAMPLE: 2026-04-30]
[EXAMPLE: CI-2026-002] | [EXAMPLE: 2026-01-22] | [EXAMPLE: Risk Committee] | [EXAMPLE: KPI/KRI Review] | [EXAMPLE: ITGC-KRI-Q4-2025] | [EXAMPLE: EDM03] | [EXAMPLE: Risk optimisation] | [EXAMPLE: IT Risk Reporting Standard] | [EXAMPLE: IT risk reports do not clearly show overdue treatment actions by accountable executive.] | [EXAMPLE: Reporting template does not include executive accountability or ageing thresholds.] | [EXAMPLE: Revise the IT risk dashboard to include overdue treatment actions, ageing, accountable executive, and escalation status.] | [EXAMPLE: Executive governance bodies receive transparent and actionable IT risk information.] | [EXAMPLE: Improved oversight of overdue IT risk treatment actions.] | [EXAMPLE: Medium] | [EXAMPLE: Medium] | [EXAMPLE: Low] | [EXAMPLE: Head of IT Risk] | [EXAMPLE: Chief Risk Officer] | [EXAMPLE: 2026-02-10] | [EXAMPLE: 2026-03-15] | [EXAMPLE: ] | [EXAMPLE: ] | [EXAMPLE: Approved] | [EXAMPLE: Green] | [EXAMPLE: Approved by Risk Committee; implementation scheduled for next reporting cycle.] | [EXAMPLE: GRC reporting configuration change] | [EXAMPLE: GRC analyst support] | [EXAMPLE: Number of overdue IT risk treatment actions without executive owner] | [EXAMPLE: 14] | [EXAMPLE: 0] | [EXAMPLE: ] | [EXAMPLE: GRC Platform/Risk Dashboards/IT Risk Committee] | [EXAMPLE: Dashboard review and committee confirmation] | [EXAMPLE: Enterprise Risk Manager] | [EXAMPLE: ] | [EXAMPLE: Not Ready] | [EXAMPLE: ] | [EXAMPLE: ] | [EXAMPLE: ] | [EXAMPLE: 2026-04-15]

## Column Guidance
Column | What to enter
Improvement ID | Enter a unique identifier for the improvement action, using a consistent format such as CI-YYYY-###.
Date Raised | Enter the date the improvement was identified in YYYY-MM-DD format.
Raised By | Enter the name or role of the person, committee, audit team, or governance body that raised the improvement.
Source of Improvement | Select the origin of the improvement: Internal Audit, External Audit, Risk Assessment, Control Testing, KPI/KRI Review, Management Review, Incident/Post-Incident Review, Regulatory Finding, COBIT Capability Assessment, Stakeholder Feedback, or Other.
Source Reference | Enter the reference to the originating record, such as audit finding ID, risk ID, incident ID, assessment report section, meeting minute reference, or ticket number.
COBIT 2019 Objective | Enter the relevant COBIT 2019 objective reference, especially EDM or MEA objectives, e.g. EDM01, EDM02, EDM03, EDM04, EDM05, MEA01, MEA02, MEA03, or MEA04.
Governance/Management Area | Enter the governance or management area affected, such as governance framework, benefits delivery, risk optimisation, resource optimisation, stakeholder transparency, performance monitoring, internal control, compliance, or assurance.
Related Policy/Process/Control | Enter the specific internal policy, process, control, standard, procedure, or framework element affected by the improvement.
Current Issue or Gap | Describe the current weakness, deficiency, inefficiency, nonconformity, or improvement opportunity in clear audit-ready language.
Root Cause | Enter the underlying cause of the issue, such as unclear ownership, missing process, inadequate control design, inconsistent execution, tooling limitation, insufficient training, resource constraint, or data quality issue.
Improvement Action | Describe the specific corrective or improvement action to be completed, using clear action-oriented wording.
Expected Outcome | Describe the intended result of the improvement, including how governance, control effectiveness, monitoring, assurance, risk reduction, transparency, or performance will improve.
Risk or Opportunity Addressed | Enter the associated risk, control weakness, regulatory obligation, performance issue, or improvement opportunity addressed by the action.
Priority | Select one value: Critical, High, Medium, Low.
Impact | Select one value: High, Medium, Low, based on expected governance, risk, compliance, operational, or stakeholder impact.
Effort | Select one value: High, Medium, Low, based on estimated implementation effort, cost, resource demand, or complexity.
Action Owner | Enter the named individual or role responsible for implementing the improvement action.
Accountable Executive | Enter the senior accountable role or governance owner responsible for ensuring the action is completed, such as CIO, CISO, Head of IT Governance, Risk Owner, or Process Owner.
Target Start Date | Enter the planned start date in YYYY-MM-DD format.
Target Completion Date | Enter the planned completion date in YYYY-MM-DD format.
Actual Start Date | Enter the actual start date in YYYY-MM-DD format; leave blank until work has started.
Actual Completion Date | Enter the actual completion date in YYYY-MM-DD format; leave blank until fully implemented.
Status | Select one value: New, Approved, In Progress, On Hold, Implemented Pending Validation, Closed, Rejected, Superseded.
RAG | Select one value: Red, Amber, Green, based on delivery health against target date, scope, dependency, and risk.
Progress Commentary | Enter concise current progress notes, including key actions completed, blockers, decisions needed, or reason for delay.
Dependencies | Enter any dependency required to complete the action, such as another project, system change, budget approval, third-party input, policy approval, or resource availability; enter None if not applicable.
Resources Required | Enter required people, budget, tools, data, training, or external support needed to complete the action.
Success Measure/KPI | Enter the metric or test that will prove the improvement has worked, such as control pass rate, audit issue reduction, SLA achievement, assessment score, reporting timeliness, or evidence completeness.
Baseline Value | Enter the starting measurement before improvement, including units or percentage where applicable, e.g. 65%, 12 open findings, 10 days, or Not measured.
Target Value | Enter the intended target measurement after implementation, including units or percentage where applicable, e.g. 95%, 0 overdue actions, 5 days.
Post-Implementation Result | Enter the measured result after implementation and validation, including units or percentage; leave blank until measured.
Evidence Location | Enter the document repository link, GRC record, ticket reference, SharePoint path, audit evidence ID, or system location where implementation evidence is stored.
Validation Method | Select or describe how completion will be verified, such as control retest, management attestation, evidence review, KPI review, audit validation, walkthrough, or sample testing.
Validator | Enter the independent person or role that validates completion, such as IT Governance Manager, Internal Audit, Risk Manager, Control Owner, Compliance Officer, or Assurance Lead.
Validation Date | Enter the date validation was completed in YYYY-MM-DD format; leave blank until validated.
Closure Decision | Select one value: Not Ready, Accepted and Closed, Rework Required, Risk Accepted, Cancelled, Superseded.
Closure Approval By | Enter the name or role approving closure of the improvement action.
Closure Approval Date | Enter the closure approval date in YYYY-MM-DD format; leave blank until closure is approved.
Lessons Learned | Enter any lessons learned, recurring themes, process improvements, or preventive actions identified during implementation.
Next Review Date | Enter the next scheduled review date in YYYY-MM-DD format, especially where the improvement requires monitoring after closure.

## Notes
Maintenance
The Continual Improvement Register is owned by the IT Governance Manager, with action updates provided by assigned action owners and closure validated by IT Risk, Compliance, or Internal Audit as appropriate. It is updated at least monthly and after each audit, assessment, control review, KPI/KRI review, incident review, or governance committee meeting, drawing from the GRC platform, audit management system, risk register, control testing records, incident system, and governance committee minutes.