## Template
Remediation ID | SWIFT CSCF Version | CSCF Control Reference | Control Title | Control Type | Applicability | Assessment Source | Gap Statement | Affected Scope | Root Cause | Risk Rating | Remediation Objective | Remediation Action | Interim Compensating Control | Action Owner | Business Owner | Technology Owner | Target Start Date | Target Completion Date | Regulatory or SWIFT Deadline | Current Status | Percent Complete | Dependencies | Required Resources or Budget | Expected Evidence | Evidence Repository Link | Validation Method | Independent Validator | Validation Date | Closure Approval | Closure Date | Residual Risk After Remediation | Exception or Deferral Reference | Last Updated Date | Comments
[EXAMPLE: CSCF-RP-2025-001] | [EXAMPLE: 2025] | [EXAMPLE: 1.1] | [EXAMPLE: SWIFT Environment Protection] | [EXAMPLE: Mandatory] | [EXAMPLE: Applicable] | [EXAMPLE: Internal CSCF Assessment] | [EXAMPLE: Network segmentation evidence for the secure zone is incomplete for one connectivity path.] | [EXAMPLE: Production SWIFT secure zone, firewall FW-SWIFT-01, Alliance Access environment] | [EXAMPLE: Firewall rule review procedure does not require mapping to CSCF zones.] | [EXAMPLE: High] | [EXAMPLE: Confirm and evidence that SWIFT-related systems are segregated from general IT networks in line with the approved architecture.] | [EXAMPLE: Review firewall rules, update network diagram, remove unauthorised flows, obtain change approval, and store evidence.] | [EXAMPLE: Daily firewall log monitoring for unexpected traffic until rule review is completed.] | [EXAMPLE: Network Security Lead] | [EXAMPLE: Head of Payments Operations] | [EXAMPLE: Infrastructure Manager] | [EXAMPLE: 2025-02-01] | [EXAMPLE: 2025-03-15] | [EXAMPLE: 2025-06-30] | [EXAMPLE: In Progress] | [EXAMPLE: 40] | [EXAMPLE: Change ticket approval CHG0001234] | [EXAMPLE: Network engineer availability and firewall vendor support] | [EXAMPLE: Approved network diagram, firewall rule export, change ticket, and segmentation test results] | [EXAMPLE: https://repository.example.com/swift/cscf/remediation/CSCF-RP-2025-001] | [EXAMPLE: Configuration review and sample traffic test by second-line security assurance] | [EXAMPLE: Security Assurance Manager] | [EXAMPLE: 2025-03-20] | [EXAMPLE: CISO] | [EXAMPLE: 2025-03-25] | [EXAMPLE: Low] | [EXAMPLE: Not Applicable] | [EXAMPLE: 2025-02-15] | [EXAMPLE: Awaiting approved maintenance window for final rule change.]
[EXAMPLE: CSCF-RP-2025-002] | [EXAMPLE: 2025] | [EXAMPLE: 5.1] | [EXAMPLE: Logical Access Control] | [EXAMPLE: Mandatory] | [EXAMPLE: Applicable] | [EXAMPLE: External Assessment] | [EXAMPLE: Quarterly privileged access review is not consistently evidenced for all SWIFT application administrators.] | [EXAMPLE: Alliance Access administrators and operating system privileged accounts] | [EXAMPLE: Access review ownership and evidence retention requirements were not formally defined.] | [EXAMPLE: Medium] | [EXAMPLE: Establish repeatable privileged access review with retained evidence and timely revocation of inappropriate access.] | [EXAMPLE: Define review procedure, generate privileged account listing, complete owner review, remove unnecessary access, and retain approval evidence.] | [EXAMPLE: Weekly monitoring of privileged account changes by IAM team.] | [EXAMPLE: IAM Operations Lead] | [EXAMPLE: Payments Operations Manager] | [EXAMPLE: SWIFT Application Owner] | [EXAMPLE: 2025-01-20] | [EXAMPLE: 2025-02-28] | [EXAMPLE: 2025-06-30] | [EXAMPLE: Completed Pending Validation] | [EXAMPLE: 90] | [EXAMPLE: HR leaver feed reconciliation and application account export availability] | [EXAMPLE: IAM analyst time and GRC workflow configuration] | [EXAMPLE: Privileged account report, review sign-off, revocation tickets, and updated access review procedure] | [EXAMPLE: https://grc.example.com/issues/CSCF-RP-2025-002] | [EXAMPLE: Sample test of privileged accounts against approved access review evidence] | [EXAMPLE: Internal Control Testing Team] | [EXAMPLE: 2025-03-05] | [EXAMPLE: SWIFT Security Officer] | [EXAMPLE: 2025-03-08] | [EXAMPLE: Low] | [EXAMPLE: Not Applicable] | [EXAMPLE: 2025-02-28] | [EXAMPLE: First quarterly review completed; validation scheduled with control testing team.]

## Column Guidance
Column | What to enter
Remediation ID | Enter a unique identifier for the remediation item, using a consistent format such as CSCF-RP-YYYY-NNN.
SWIFT CSCF Version | Enter the SWIFT CSCF version the remediation relates to, for example 2024, 2025, or the full framework version used for attestation.
CSCF Control Reference | Enter the exact SWIFT CSCF control reference being remediated, for example 1.1, 1.2, 2.1, 2.9, 4.1, 5.1, 6.4, or 7.1.
Control Title | Enter the official or organisation-adopted title of the SWIFT CSCF control being remediated.
Control Type | Enter one of: Mandatory, Advisory, Not Applicable. For this remediation plan, mandatory-control gaps should normally be recorded as Mandatory.
Applicability | Enter the applicability decision for the control in the organisation’s SWIFT architecture context, using one of: Applicable, Not Applicable, Partially Applicable.
Assessment Source | Enter the source that identified the gap, such as Internal CSCF Assessment, External Assessment, Independent Assessment, Audit Finding, Penetration Test, Vulnerability Assessment, or Management Review.
Gap Statement | Describe the specific control gap to be closed, stating what is missing, incomplete, ineffective, or not evidenced; avoid generic statements.
Affected Scope | Identify the affected SWIFT environment, architecture type, systems, applications, infrastructure, users, locations, service providers, or processes.
Root Cause | State the primary cause of the gap, such as missing procedure, incomplete implementation, legacy configuration, tooling limitation, resource constraint, ownership gap, or third-party dependency.
Risk Rating | Enter the current risk rating before remediation using one of: Critical, High, Medium, Low, or according to the organisation’s approved risk methodology.
Remediation Objective | State the intended compliant end state that will close the CSCF gap and enable audit evidence to be produced.
Remediation Action | Describe the specific action or set of actions to be completed, including configuration, process, technology, governance, evidence, or testing activities.
Interim Compensating Control | Describe any temporary mitigating measure in place until full remediation is complete; enter None if no compensating control exists.
Action Owner | Enter the named person or role accountable for completing the remediation action.
Business Owner | Enter the business process owner accountable for accepting the remediation outcome and related operational impact.
Technology Owner | Enter the IT, security, infrastructure, application, or service owner responsible for technical implementation.
Target Start Date | Enter the planned remediation start date in YYYY-MM-DD format.
Target Completion Date | Enter the planned remediation completion date in YYYY-MM-DD format.
Regulatory or SWIFT Deadline | Enter the required deadline in YYYY-MM-DD format if driven by SWIFT attestation, regulator, audit commitment, or management-approved milestone; otherwise enter Not Applicable.
Current Status | Enter one of: Not Started, In Progress, Blocked, Completed Pending Validation, Validated, Closed, Deferred, Cancelled.
Percent Complete | Enter the estimated completion percentage as a whole number from 0 to 100.
Dependencies | Record any prerequisite activities, approvals, systems, vendors, change tickets, procurement, or related remediation items; enter None if no dependencies exist.
Required Resources or Budget | Enter required people, technology, vendor support, funding, or budget reference needed to complete the remediation; enter None if not applicable.
Expected Evidence | List the evidence expected to prove remediation, such as approved policy, configuration export, screenshot, access review, test result, change record, monitoring alert, procedure, or independent validation report.
Evidence Repository Link | Enter the controlled repository path, GRC record link, SharePoint link, ticket link, or document management reference where evidence will be stored.
Validation Method | Describe how closure will be verified, such as control re-test, configuration review, sample testing, walkthrough, vulnerability scan, access recertification, or independent assessment.
Independent Validator | Enter the named person, team, second-line function, internal audit, external assessor, or qualified independent reviewer responsible for validating closure.
Validation Date | Enter the date validation was completed in YYYY-MM-DD format; leave blank until validation is performed.
Closure Approval | Enter the name and role of the person approving closure, such as CISO, SWIFT Security Officer, Control Owner, Risk Owner, or Steering Committee chair.
Closure Date | Enter the formal closure date in YYYY-MM-DD format; leave blank until approved for closure.
Residual Risk After Remediation | Enter the expected or confirmed residual risk after remediation using one of: Critical, High, Medium, Low, None, or Not Assessed.
Exception or Deferral Reference | Enter the approved risk acceptance, exception, or deferral reference if remediation will not be completed by the deadline; otherwise enter Not Applicable.
Last Updated Date | Enter the date this remediation item was last updated in YYYY-MM-DD format.
Comments | Enter concise additional notes, decisions, blockers, meeting outcomes, or clarifications relevant to remediation tracking.

## Notes
Maintenance
Owned by the SWIFT Security Officer or CSCF remediation programme manager, with updates at least weekly during remediation and monthly thereafter until all items are closed. The template draws from CSCF self-assessment results, independent assessment reports, audit findings, GRC issue records, change management tickets, vulnerability tools, IAM records, and evidence repositories.