COMPLYVERSE  |  CRITICAL PATH ANALYSIS

Recovery Sequence Documentation — SBP ETGRMF Business Continuity Evidence

| Document Ref CV-BCP-CPA-002 | Effective Date March 28, 2025 | Review Cycle Annual / Post-DR Test | Framework Ref SBP ETGRMF — BCP / DR Controls |
| --- | --- | --- | --- |

1. PURPOSE

This Critical Path Analysis (CPA) documents the formally approved recovery sequence for each Tier 1 (mission-critical) system of DemoTech Enterprises (Pvt.) Ltd. It defines the ordered set of recovery tasks, responsible parties, and time-bound milestones that must be executed to restore operations within the agreed RTO.

This document is maintained as evidence of BCP planning maturity under the SBP Enterprise Technology Governance & Risk Management Framework (ETGRMF), and is tested through quarterly DR exercises.

2. CRITICAL PATH METHODOLOGY

The critical path is defined as the minimum sequence of dependent activities that, if delayed, will cause the overall RTO to be breached. Each path below represents the longest-duration chain of recovery activities for the given system. Non-critical parallel tasks are excluded from the critical path but documented in system-specific DR runbooks.

| Principle | Description |
| --- | --- |
| Single Dependency Rule | No recovery step on the critical path may begin until its predecessor is fully completed and validated. |
| Time-Boxing | Each step carries a maximum time allocation. Breach of any step's time box triggers escalation to the Incident Commander. |
| Escalation Triggers | If cumulative time-to-restore reaches 75% of RTO without reaching validation phase, immediate escalation to CISO and CEO is mandated. |
| Rollback Gate | At Step 3 (DR Spinup), a binary go/no-go decision is made. If DR environment is deemed unstable, rollback to primary is attempted if feasible. |

3. CRITICAL PATH RECOVERY SEQUENCES

Payment Processing Engine (RTO: 1 hr)

| Time Window | # | Recovery Step | Actions & Acceptance Criteria |
| --- | --- | --- | --- |
| 0:00–0:05 | 1 | Incident Detection & Alert | Automated monitoring (Nagios/Zabbix) triggers P1 alert to on-call team |
| 0:05–0:15 | 2 | Incident Declaration | CISO or IT Lead declares BCP event; Incident Commander assigned |
| 0:15–0:20 | 3 | DR Failover Initiation | DR runbook activated; replication status verified |
| 0:20–0:35 | 4 | DR Environment Spinup | Hot standby promoted; DNS cutover executed |
| 0:35–0:50 | 5 | Validation & Smoke Testing | Transaction processing validated at DR; reconciliation checks run |
| 0:50–1:00 | 6 | Stakeholder Notification & Handoff | SBP, senior management, and partners notified; handoff to operations |

Internet Banking Portal (RTO: 2 hrs)

| Time Window | # | Recovery Step | Actions & Acceptance Criteria |
| --- | --- | --- | --- |
| 0:00–0:10 | 1 | Incident Detection & Triage | WAF/APM alert; triage confirms full outage |
| 0:10–0:20 | 2 | Incident Declaration | BCP event declared; war room convened (virtual/physical) |
| 0:20–0:50 | 3 | DR Failover & Load Balancer Reconfiguration | Traffic rerouted to DR; SSL certificates validated |
| 0:50–1:20 | 4 | Application Layer Restoration | App servers started; database connections verified |
| 1:20–1:45 | 5 | End-to-End Functional Testing | Login, transfer, statement flows tested; security scan run |
| 1:45–2:00 | 6 | Go-Live & Communication | DR site opened to customers; customer notice published |

Core Banking System — T24 (RTO: 4 hrs)

| Time Window | # | Recovery Step | Actions & Acceptance Criteria |
| --- | --- | --- | --- |
| 0:00–0:15 | 1 | Detection & P1 Declaration | Automated health checks fail; on-call DBA and vendor support engaged |
| 0:15–0:30 | 2 | Root Cause Assessment | Rapid triage: hardware, software, or data corruption determined |
| 0:30–1:30 | 3 | DR Activation & Data Integrity Check | Warm standby activated; last known-good checkpoint identified; data integrity verified |
| 1:30–2:30 | 4 | Core Banking Restoration | T24 services restored at DR; GL and accounts reconciled |
| 2:30–3:30 | 5 | Peripheral System Reconnection | ATM, payment, SWIFT gateways reconnected to restored T24 |
| 3:30–4:00 | 6 | Parallel Run & Sign-off | Parallel validation; IT Head and CISO sign off for full resumption |

4. ROLES & RESPONSIBILITIES ON CRITICAL PATH

| Role | Assignee | Critical Path Responsibilities |
| --- | --- | --- |
| Incident Commander | CISO — Mr. Imran Ali | Declares BCP event; makes go/no-go decisions; coordinates all recovery teams; communicates to Board |
| IT Recovery Lead | Head of IT — Mr. Tariq Hussain | Executes technical failover steps; owns DR runbooks; validates system restoration |
| Database Administrator | DBA Team Lead — Mr. Asif Raza | Validates data integrity at each DR checkpoint; confirms RPO compliance |
| Network Engineer | Network Lead — Ms. Hina Shah | Executes DNS cutover, BGP failover, and connectivity validation |
| Business Representative | COO / Branch Ops Head | Validates business process functionality; authorises go-live at DR site |
| Vendor Support | T24 / Core System Vendor | On-call L3 support for core banking restoration (contracted SLA) |

5. DR TEST HISTORY

| Test Date | Systems Tested | Test Type | Achieved RTO | Result |
| --- | --- | --- | --- | --- |
| Sep 15, 2024 | Payment Engine, Internet Banking | Full Failover | 1hr 45min | PASS |
| Dec 10, 2024 | Core Banking (T24) | Tabletop + Partial | 3hr 50min | PASS |
| Jan 22, 2025 | Network & Infrastructure | Full Failover | 1hr 10min | PASS |
| Mar 5, 2025 | All Tier 1 Systems | Full DR Exercise | See BIA Report | PASS |

6. APPROVAL

| Incident Commander / CISO Mr. Imran Ali Date Signed: March 28, 2025 | Head of IT Operations Mr. Tariq Hussain Date Signed: March 28, 2025 |
| --- | --- |

Official Use Only  |  Document Ref: CV-BCP-CPA-002  |  ComplyVerse GRC Platform  |  SBP ETGRMF Evidence