## PCI_DSS_Backend_Tasks
Epic | Story | Task Name | Description | Type | Priority
Pipeline Validation | End-to-End Testing | Replit End-to-End Test | Run full backend pipeline on Replit for 24 hours to ensure stability and completion. | Task | High
Database & Schema | Database Validation | Validate PCI DSS Requirements Table | Verify pci_dss_requirements table contains exactly 124 rows. | Task | High
Database & Schema | Database Validation | Validate Required Evidence Schema | Check required_evidence schema fields and data types. | Task | High
Database & Schema | Schema Design | Decide Control Table Strategy | Decide whether to introduce controls table or keep requirements as controls. | Task | Medium
Evidence Engine | Dry Run | Evidence Population Dry Run | Run populate_required_evidence.py with limit=10 and validate JSON structure. | Task | High
Evidence Engine | Full Population | Full Evidence Population Run | Populate required evidence for all 124 PCI DSS requirements. | Task | High
Evidence Engine | Validation | Validate Evidence Records | Verify row count, timestamps, and data integrity after population. | Task | High
Schema Normalization | Optional Refactor | Create Controls Table | Create controls table for 12 PCI DSS high-level controls. | Task | Medium
Schema Normalization | Optional Refactor | Requirement-Control Mapping | Create control_requirement_map table and link requirements. | Task | Medium
API Layer | Controls APIs | Develop Controls APIs | Implement GET controls, control details, and controls with evidence endpoints. | Task | High
API Layer | Gap Analysis | Gap Analysis Endpoint | Develop /api/controls/{id}/gap endpoint. | Task | High
API Layer | Evidence APIs | Evidence Upload & Review API | Implement evidence upload and PATCH review endpoint with auto findings. | Task | High
API Layer | Findings & Risks | Findings & Risks APIs | Implement CRUD APIs for findings and risks. | Task | High
Reporting | Compliance Reports | ROC & AOC Report APIs | Generate ROC and AOC reports (HTML to PDF). | Task | Medium
Monitoring | Scheduled Jobs | Quarterly Monitoring Job | Configure APScheduler for quarterly compliance scans. | Task | High
Monitoring | Automation | Auto-Create Findings | Auto-generate findings when evidence is stale. | Task | High
Testing | Backend Validation | Status Transition Testing | Test compliance status transitions across controls. | Task | High
Testing | Monitoring Validation | Manual Monitoring Run | Trigger monitoring manually and verify auto findings. | Task | High