## Template
Register ID | Entry Type | Date Raised | Raised By | FM Domain | Facility / Asset / Service Scope | Process / Activity | Issue / Context Source | Interested Party / Requirement Affected | Risk or Opportunity Statement | Cause / Driver | Potential Consequence / Benefit | ISO 41001 Clause / FMS Objective Link | Existing Controls / Current Arrangements | Likelihood Rating | Impact Rating | Inherent Score | Inherent RAG | Treatment / Response Strategy | Planned Actions | Action Owner | Target Completion Date | Resources Required | Residual Likelihood Rating | Residual Impact Rating | Residual Score | Residual RAG | Evaluation Method | Effectiveness Criteria | Review Frequency | Current Status | Last Review Date | Next Review Date | Evidence / Record Reference | Related Incident / Audit / Change Reference | Escalation Required | Approval Authority | Closure Date | Closure Rationale / Lessons Learned
[EXAMPLE: FMR-2026-001] | [EXAMPLE: Risk] | [EXAMPLE: 2026-01-15] | [EXAMPLE: Jane Smith, Facilities Compliance Manager] | [EXAMPLE: Hard FM] | [EXAMPLE: HQ Building - HVAC chillers] | [EXAMPLE: Planned preventive maintenance] | [EXAMPLE: Asset condition survey] | [EXAMPLE: Occupants; statutory workplace comfort requirements; SLA HVAC-01] | [EXAMPLE: If ageing chiller components fail during peak summer, then indoor environmental conditions may fall below agreed service levels and disrupt occupant productivity.] | [EXAMPLE: Obsolete components and extended lead times for replacement parts] | [EXAMPLE: Service interruption, comfort complaints, increased emergency repair cost, potential SLA breach] | [EXAMPLE: ISO 41001 Cl. 6.1; FM Objective OBJ-03 Service Continuity] | [EXAMPLE: Quarterly PPM, BMS alarms, critical spares list, maintenance contractor call-out] | [EXAMPLE: 4] | [EXAMPLE: 4] | [EXAMPLE: 16] | [EXAMPLE: Red] | [EXAMPLE: Reduce/Mitigate] | [EXAMPLE: Complete lifecycle replacement options appraisal, approve critical spares purchase, update contingency cooling plan, include chiller renewal in capital plan.] | [EXAMPLE: Head of Engineering] | [EXAMPLE: 2026-04-30] | [EXAMPLE: Capital budget approval; specialist contractor; procurement support] | [EXAMPLE: 2] | [EXAMPLE: 3] | [EXAMPLE: 6] | [EXAMPLE: Amber] | [EXAMPLE: Review PPM compliance, BMS alarm frequency, cooling-related complaints, and approved capital plan status.] | [EXAMPLE: Zero critical chiller outages during cooling season and contingency plan tested by 2026-05-31.] | [EXAMPLE: Quarterly] | [EXAMPLE: Action Planned] | [EXAMPLE: 2026-01-20] | [EXAMPLE: 2026-04-01] | [EXAMPLE: Asset Survey AS-2026-014; Work Order WO-456789] | [EXAMPLE: Audit Finding IA-2026-02] | [EXAMPLE: Yes] | [EXAMPLE: FM Director] | [EXAMPLE: ] | [EXAMPLE: ]
[EXAMPLE: FMR-2026-002] | [EXAMPLE: Opportunity] | [EXAMPLE: 2026-02-03] | [EXAMPLE: Ahmed Khan, Workplace Services Lead] | [EXAMPLE: Soft FM] | [EXAMPLE: Multi-site cleaning contract] | [EXAMPLE: Cleaning service delivery and resource planning] | [EXAMPLE: Supplier performance review] | [EXAMPLE: Occupants; client organisation; sustainability objective] | [EXAMPLE: If cleaning schedules are adjusted using occupancy data, then service quality and resource efficiency may improve while reducing chemical and labour waste.] | [EXAMPLE: Hybrid working has reduced occupancy on some floors on specific days] | [EXAMPLE: Cost saving, improved user satisfaction, reduced environmental impact, better alignment of service levels to demand] | [EXAMPLE: ISO 41001 Cl. 6.1; FM Objective OBJ-05 Resource Efficiency] | [EXAMPLE: Fixed cleaning specification, monthly supplier KPI review, helpdesk feedback monitoring] | [EXAMPLE: 3] | [EXAMPLE: 3] | [EXAMPLE: 9] | [EXAMPLE: Amber] | [EXAMPLE: Enhance] | [EXAMPLE: Pilot occupancy-based cleaning on two floors, update cleaning specification, agree revised KPIs with supplier, monitor feedback and cost data.] | [EXAMPLE: Soft Services Manager] | [EXAMPLE: 2026-05-31] | [EXAMPLE: Occupancy analytics access; supplier variation approval; communications to occupants] | [EXAMPLE: 4] | [EXAMPLE: 4] | [EXAMPLE: 16] | [EXAMPLE: Green] | [EXAMPLE: Compare cleaning complaints, audit scores, labour hours, consumables usage, and cost against baseline.] | [EXAMPLE: Maintain cleaning audit score above 95%, reduce consumables by 10%, and no increase in complaints over pilot period.] | [EXAMPLE: Monthly] | [EXAMPLE: In Progress] | [EXAMPLE: 2026-03-01] | [EXAMPLE: 2026-04-01] | [EXAMPLE: Supplier Review SR-2026-03; KPI Dashboard KPI-CLEAN-01] | [EXAMPLE: Change Request CR-2026-011] | [EXAMPLE: No] | [EXAMPLE: Head of Facilities Operations] | [EXAMPLE: ] | [EXAMPLE: ]

## Column Guidance
Column | What to enter
Register ID | Enter a unique identifier for the entry using a consistent format, e.g. FMR-YYYY-###.
Entry Type | Select one allowed value: Risk, Opportunity, Risk and Opportunity.
Date Raised | Enter the date the entry was first recorded in YYYY-MM-DD format.
Raised By | Enter the name and role/team of the person raising the entry.
FM Domain | Select the main FM area affected: Hard FM, Soft FM, Lifecycle/Asset Management, HSE, Energy/Sustainability, Security, Space/Workplace, Contract/Supplier, Business Continuity, Other.
Facility / Asset / Service Scope | Enter the specific site, building, zone, asset class, service contract, or FM service scope affected.
Process / Activity | Enter the FM process or activity where the risk/opportunity arises, e.g. planned maintenance, cleaning, catering, statutory inspection, lifecycle planning, helpdesk, contractor management.
Issue / Context Source | State the source that identified the issue, e.g. context review, interested-party need, compliance obligation, asset condition survey, incident, audit finding, customer feedback, supplier review, strategic planning.
Interested Party / Requirement Affected | Identify the stakeholder or requirement affected, e.g. occupants, client, landlord, regulator, service provider, insurer, community, legal/statutory requirement, SLA/KPI.
Risk or Opportunity Statement | Write a clear statement of the uncertain event or condition and its effect on intended FM outcomes; use format: If/when [event/condition], then [impact/benefit] to [FM objective/service outcome].
Cause / Driver | Enter the underlying cause, trigger, vulnerability, trend, or enabling factor creating the risk or opportunity.
Potential Consequence / Benefit | Describe the credible negative consequence for risks or positive benefit for opportunities, including effects on compliance, safety, service continuity, cost, asset performance, user experience, sustainability, or lifecycle value.
ISO 41001 Clause / FMS Objective Link | Enter the relevant ISO 41001 clause, FM objective, policy commitment, compliance obligation, or KPI/SLA reference that this entry could affect.
Existing Controls / Current Arrangements | Describe current measures already in place, such as procedures, inspections, PPM, competency controls, monitoring, contracts, contingency plans, permits, audits, or technology systems.
Likelihood Rating | Enter a numeric rating using the organisation's approved scale, typically 1-5 where 1 = Rare and 5 = Almost Certain; define consistently in the workbook legend.
Impact Rating | Enter a numeric rating using the organisation's approved scale, typically 1-5 where 1 = Insignificant and 5 = Severe/Major; consider safety, compliance, service, financial, reputation, asset, and environmental impact.
Inherent Score | Enter the calculated pre-treatment score, usually Likelihood Rating x Impact Rating; numeric value only.
Inherent RAG | Enter the inherent priority band using allowed values: Red, Amber, Green, based on the organisation's approved risk matrix thresholds.
Treatment / Response Strategy | Select the intended response: Avoid, Reduce/Mitigate, Transfer/Share, Accept, Exploit, Enhance, Monitor, Contingency Plan, Other.
Planned Actions | Describe specific actions to address the risk or opportunity and how they will be integrated into FM processes, plans, contracts, resources, or controls.
Action Owner | Enter the accountable role/person responsible for completing the planned actions, not a department only.
Target Completion Date | Enter the agreed completion date for planned actions in YYYY-MM-DD format.
Resources Required | Enter required budget, labour, contractor support, system changes, materials, training, or management approval needed to implement the action.
Residual Likelihood Rating | Enter the expected or confirmed likelihood rating after treatment using the same scale as Likelihood Rating.
Residual Impact Rating | Enter the expected or confirmed impact rating after treatment using the same scale as Impact Rating.
Residual Score | Enter the calculated post-treatment score, usually Residual Likelihood Rating x Residual Impact Rating; numeric value only.
Residual RAG | Enter the residual priority band using allowed values: Red, Amber, Green, based on the approved risk matrix thresholds.
Evaluation Method | State how effectiveness of the action/control will be evaluated, e.g. KPI trend, audit, inspection result, incident reduction, statutory compliance evidence, customer satisfaction, cost saving, energy data, lifecycle analysis.
Effectiveness Criteria | Enter measurable success criteria that demonstrate the action has addressed the risk/opportunity, including target value, threshold, or pass/fail condition where possible.
Review Frequency | Select how often the entry must be reviewed: Monthly, Quarterly, Six-Monthly, Annually, Event-Driven, Project Milestone, Other.
Current Status | Select one allowed value: New, Assessed, Action Planned, In Progress, Overdue, Monitoring, Escalated, Closed, Deferred.
Last Review Date | Enter the most recent review date in YYYY-MM-DD format; leave blank only for newly raised entries not yet reviewed.
Next Review Date | Enter the next planned review date in YYYY-MM-DD format, based on risk level, status, and review frequency.
Evidence / Record Reference | Enter document IDs, system links, work order numbers, inspection reports, audit records, meeting minutes, photos, dashboards, or other evidence supporting assessment and action status.
Related Incident / Audit / Change Reference | Enter any linked incident, nonconformity, audit finding, change request, project, asset survey, or management review reference; enter N/A if none.
Escalation Required | Select Yes or No; select Yes where residual exposure, resource need, compliance risk, or decision authority exceeds local FM authority.
Approval Authority | Enter the role or governance body required to approve the assessment, treatment plan, acceptance of residual risk, or opportunity investment, e.g. FM Director, Client Representative, Risk Committee.
Closure Date | Enter the date closed in YYYY-MM-DD format; leave blank until the entry is formally closed.
Closure Rationale / Lessons Learned | Record why the entry was closed, evidence that effectiveness criteria were met, residual risk acceptance, benefits realised, and any lessons to feed into FM planning or management review.

## Notes
Maintenance
The FM Risk & Opportunity Register is owned by the Facilities Management System Manager or FM Risk Owner, with accountable review by FM leadership. It should be updated when new risks/opportunities, incidents, audits, changes, projects, asset surveys, supplier reviews, or management reviews occur, and formally reviewed at least quarterly using data from the CAFM/IWMS, helpdesk, asset register, compliance tracker, audit system, incident system, supplier performance reports, and management review outputs.