## Template
Incident Record ID | Date/Time Detected | Detected By | Detection Source | Incident Status | Incident Category | Suspected or Known Incident | Incident Summary | Systems, Applications, or Locations Affected | ePHI Involved | Type of ePHI Potentially Involved | Estimated Individuals Affected | Initial Severity | Incident Owner | Date/Time Escalated to Incident Response Team | Immediate Containment Actions | Response Actions Taken | Mitigation Actions Taken | Harmful Effects Identified | Harmful Effects Mitigated | Root Cause | Corrective Actions Required | Corrective Action Owner | Corrective Action Due Date | Corrective Action Completion Date | Breach Assessment Required | Breach Assessment Reference | Notifications Required | Notifications Completed | Evidence Location | Outcome / Closure Summary | Date/Time Closed | Closed By | Management Review Date
[EXAMPLE: IR-2026-001] | [EXAMPLE: 2026-02-14 09:32 EST] | [EXAMPLE: EDR platform] | [EXAMPLE: EDR alert] | [EXAMPLE: Closed] | [EXAMPLE: Malware/Ransomware] | [EXAMPLE: Known] | [EXAMPLE: Malware detected on one billing workstation; endpoint isolated and investigated.] | [EXAMPLE: WS-BILL-014; Billing Department] | [EXAMPLE: Unknown] | [EXAMPLE: Patient name, billing account number, insurance ID potentially accessible on workstation] | [EXAMPLE: Unknown] | [EXAMPLE: High] | [EXAMPLE: Security Incident Manager] | [EXAMPLE: 2026-02-14 09:45 EST] | [EXAMPLE: Workstation isolated from network; user account disabled; malicious hash blocked.] | [EXAMPLE: EDR scan completed; logs reviewed; disk image collected; password reset performed.] | [EXAMPLE: Endpoint rebuilt; additional monitoring enabled; user credentials rotated.] | [EXAMPLE: Potential unauthorized access to locally cached billing data.] | [EXAMPLE: No confirmed exfiltration; endpoint rebuilt and credentials reset.] | [EXAMPLE: User opened malicious attachment bypassing email filter.] | [EXAMPLE: Update phishing training; tune email gateway attachment rules.] | [EXAMPLE: Security Awareness Lead] | [EXAMPLE: 2026-03-15] | [EXAMPLE: 2026-03-10] | [EXAMPLE: Pending] | [EXAMPLE: PRIV-RA-2026-004] | [EXAMPLE: Pending] | [EXAMPLE: Pending] | [EXAMPLE: SecureCase/IR-2026-001] | [EXAMPLE: Incident confirmed, contained, and mitigated; breach assessment pending privacy review.] | [EXAMPLE: 2026-02-20 16:10 EST] | [EXAMPLE: Security Officer] | [EXAMPLE: 2026-02-21]
[EXAMPLE: IR-2026-002] | [EXAMPLE: 2026-04-03 13:05 UTC] | [EXAMPLE: Helpdesk analyst] | [EXAMPLE: User report] | [EXAMPLE: Closed] | [EXAMPLE: Improper Disclosure] | [EXAMPLE: Known] | [EXAMPLE: Email containing patient discharge instructions sent to incorrect recipient.] | [EXAMPLE: Secure email system; Care Coordination Team] | [EXAMPLE: Yes] | [EXAMPLE: Patient name, discharge instructions, appointment details] | [EXAMPLE: 1] | [EXAMPLE: Medium] | [EXAMPLE: Privacy Officer] | [EXAMPLE: 2026-04-03 13:20 UTC] | [EXAMPLE: Recipient contacted; message recall attempted; sender instructed not to resend.] | [EXAMPLE: Email audit trail reviewed; recipient confirmed deletion; supervisor interviewed sender.] | [EXAMPLE: Written deletion confirmation obtained; care coordination email verification reminder issued.] | [EXAMPLE: Impermissible disclosure of one patient’s ePHI to unintended recipient.] | [EXAMPLE: Recipient confirmed deletion and no further disclosure.] | [EXAMPLE: Manual addressing error.] | [EXAMPLE: Reinforce recipient verification procedure during team huddle.] | [EXAMPLE: Care Coordination Manager] | [EXAMPLE: 2026-04-10] | [EXAMPLE: 2026-04-08] | [EXAMPLE: Yes] | [EXAMPLE: PRIV-RA-2026-009] | [EXAMPLE: Affected Individuals] | [EXAMPLE: Affected Individual completed 2026-04-12] | [EXAMPLE: SecureCase/IR-2026-002] | [EXAMPLE: Incident documented; harmful effects mitigated; notification completed per privacy determination.] | [EXAMPLE: 2026-04-12 15:30 UTC] | [EXAMPLE: Privacy Officer] | [EXAMPLE: 2026-04-13]

## Column Guidance
Column | What to enter
Incident Record ID | Enter a unique incident identifier using the organisation’s incident numbering format, e.g. IR-YYYY-NNN.
Date/Time Detected | Enter the date and time the incident was first identified or reported in ISO format YYYY-MM-DD HH:MM, including timezone if applicable.
Detected By | Enter the name, role, team, or automated tool that identified the suspected or known security incident.
Detection Source | Enter the source of detection, such as SIEM alert, EDR alert, helpdesk ticket, user report, audit log review, vendor notification, physical security report, or compliance review.
Incident Status | Enter the current status using allowed values: Open, Investigating, Contained, Mitigation In Progress, Pending Corrective Action, Closed, Reopened.
Incident Category | Enter the category using allowed values: Unauthorized Access, Malware/Ransomware, Phishing/Social Engineering, Lost or Stolen Device, Improper Disclosure, System Misconfiguration, Denial of Service, Insider Misuse, Third-Party Incident, Audit Log Anomaly, Other.
Suspected or Known Incident | Enter whether the event is Suspected or Known based on available evidence at the time of logging.
Incident Summary | Provide a concise factual description of what happened, how it was identified, and why it is being treated as a security incident; avoid speculation.
Systems, Applications, or Locations Affected | List affected systems, applications, databases, endpoints, networks, facilities, or business locations; use asset names or IDs where available.
ePHI Involved | Enter Yes, No, or Unknown to indicate whether electronic protected health information was involved or potentially involved.
Type of ePHI Potentially Involved | If ePHI is involved or unknown, describe the type of data potentially affected, such as patient name, MRN, DOB, diagnosis, treatment information, billing information, insurance ID, credentials, or clinical notes; enter N/A if not applicable.
Estimated Individuals Affected | Enter the estimated number of individuals whose ePHI may be affected; use a number, Unknown, or N/A.
Initial Severity | Enter severity using allowed values: Critical, High, Medium, Low; base this on impact to confidentiality, integrity, availability, ePHI exposure, operational disruption, and regulatory risk.
Incident Owner | Enter the accountable person or role responsible for coordinating the incident response, such as Security Incident Manager, Privacy Officer, Security Officer, or IT Operations Lead.
Date/Time Escalated to Incident Response Team | Enter the date and time the incident was escalated to the responsible response personnel in format YYYY-MM-DD HH:MM, or N/A if escalation was not required.
Immediate Containment Actions | Describe immediate actions taken to limit impact, such as disabling accounts, isolating endpoints, blocking IPs, revoking tokens, quarantining email, disconnecting systems, or stopping data transfer.
Response Actions Taken | Document investigation and response activities performed, including log review, forensic collection, user interviews, password resets, malware removal, system restoration, or vendor coordination.
Mitigation Actions Taken | Document specific actions taken to reduce or eliminate harmful effects of the incident, including recovery steps, data retrieval, access correction, notification support, additional monitoring, or compensating controls.
Harmful Effects Identified | Describe actual or reasonably anticipated harmful effects, such as unauthorized ePHI access, data alteration, operational downtime, malware persistence, credential compromise, or patient care disruption; enter None Identified if applicable.
Harmful Effects Mitigated | Describe how each identified harmful effect was mitigated, or enter Not Yet Mitigated with explanation if mitigation remains incomplete.
Root Cause | Enter the determined root cause, such as compromised credentials, missing patch, misconfigured permissions, user error, failed process, vendor failure, inadequate monitoring, or Unknown Pending Investigation.
Corrective Actions Required | List required follow-up actions to prevent recurrence or strengthen safeguards, such as policy update, workforce training, access review, patching, MFA enforcement, logging improvement, or vendor remediation.
Corrective Action Owner | Enter the person, role, or team accountable for completing corrective actions.
Corrective Action Due Date | Enter the target completion date for corrective actions in YYYY-MM-DD format, or N/A if no corrective action is required.
Corrective Action Completion Date | Enter the actual completion date in YYYY-MM-DD format once all corrective actions are completed, or leave blank until complete.
Breach Assessment Required | Enter Yes, No, or Pending to indicate whether a HIPAA breach risk assessment is required based on potential impermissible use or disclosure of PHI/ePHI.
Breach Assessment Reference | Enter the reference number or link to the separate breach risk assessment, privacy investigation, or legal determination record; enter N/A if not required.
Notifications Required | Enter required notifications, if any, using allowed values or descriptions: None, Affected Individuals, HHS, Media, Business Associate, Covered Entity, Law Enforcement, State Regulator, Cyber Insurer, Other.
Notifications Completed | Record notifications completed, including recipient type and completion date in YYYY-MM-DD format; enter Pending or N/A as applicable.
Evidence Location | Enter the secure repository path, ticket link, case folder, or evidence ID where supporting evidence is retained, such as logs, screenshots, emails, forensic images, approvals, and communications.
Outcome / Closure Summary | Summarize the final outcome, including whether the incident was confirmed, contained, mitigated, corrective actions completed or tracked, and any remaining accepted risk.
Date/Time Closed | Enter the date and time the incident record was formally closed in format YYYY-MM-DD HH:MM, or leave blank until closure.
Closed By | Enter the name and role of the person approving closure of the incident record.
Management Review Date | Enter the date management, Security Officer, Privacy Officer, or other authorised reviewer reviewed the incident record in YYYY-MM-DD format.

## Notes
Maintenance
The Security Officer owns this template with input from the Privacy Officer and Incident Response Manager; entries are updated in real time during incidents and reviewed at closure, with the template reviewed at least annually or after a material incident. The record draws from the incident management/ticketing system, SIEM/EDR alerts, helpdesk reports, audit logs, forensic evidence repositories, and privacy breach assessment records.