## Audit_OS_Points (hidden)
S# | Description | Source | Raised By: | Responsible | Target Completion date | Next action Item | Status
1 | During Audit it was noted that information security team has not developed security hardening/IS standard for the hardening of POS machines neither any validation has been performed to review the controls implemented on the POS machines. IS IS Comments: We will provide POS Hardening and IS standard by Q3-2022. | Control Committee Q1-2022 | IA | Farhan | Q3-2022
2 | Bahrain PT Report |  | Bahrain-Auditor | Abid | Q1-2022 |  | Completed
3 | Diligent Password and Password Expiry Date |  | IA | Shoukat Ali | Q1-2022
4 | GNB and Digital App-Audit points raised./Global Net-banking Audit (Follow up) | Control Committee Q1-2022 | IA | Bilal Tasneem | Q1-2022 | MFA / IS to share an updated status on the key issues identified in the Global Net Banking Audit Report. Timeline: April 30, 2022 | In-progress
5 | Self-Assessment Cyber Hygiene Exercise | Control Committee Q1-2022 | IA | ITG | 2022-04-30 | MFA / AMT to share an updated status on the submission of self-assessment on Cyber Hygiene Exercise to the Regulator after approval of action plan by ITSC, ISSC, BRCC and BITC. Timeline: April 10, 2022 | In-progress
6 | ATM Audit | Control Committee Q1-2022 | IA | ITG/IS | 2022-04-08 | AMT responded that IT would share the action plan in the next week for the compliance with the remaining regulatory instructions. Timeline: April 8, 2022. MFA / IS to share an updated status on the key issues identified in the ATM Audit Report. Timeline: April 30, 2022 | Pls refer point 11,12 & 13
7 | Point of Sale (POS) Audit | Control Committee Q1-2022 | IA | IT/IS/DB | 2022-04-30 | SS/MFA / IS to share an updated status on the key issues identified in the Point of Sale Audit Report. Timeline: April 30, 2022 MFA / IS to share the management response on another internal audit related to the tablets used by the RM. Timeline: April 8, 2022 | Pls refer point 14
8 | Customer Data Privacy Issue in Core Banking System:  ITG to provide updated timeline post testing of the fix by the vendor and update in next meeting.  Update on a comprehensive review of all screens to be provided by Information Technology (IT) and Information Security (IS) by next meeting | Control Committee Q1-2022 |  | IT/IS | 2022-05-31 | Not Pertain to IS
9 | Develop Security Risk Assessment and Governance Framework for third party vendors | ITSC/BITC | ITSC/BITC | IS/IT | 2022-12-31 |  | TBI
10 | Develop process for a secure Software Development Lifecycle (SDLC) | ITSC/BITC | ITSC/BITC | IS/IT | 2022-06-30 |  | In-progress
11 | ATM Security Standard (Repeat Issue) – (High Priority) | Control Committee 30-Apr-2022 | ATM Audit Report | IS | 2022-09-30 | IS team will validate the ATM Machine hardening standard by Q3-2022 | TBI
12 | Hard Disk Encryption Solution (Repeat Issue) – (High Priority) | Control Committee 30-Apr-2022 | ATM Audit Report | IS | 2022-04-30 | IS have provided the response on the Hard Disk Encryption | Completed
13 | ATM Security Logs (Repeated Issue) – (Medium Priority) | Control Committee 30-Apr-2022 | ATM Audit Report | IS | 2022-09-30 | IS team will validate the ATM security logs by Q3-2022 | TBI
14 | Hardening documents for POS machines – (Medium Risk) | Control Committee 30-Apr-2022 | POS Audit Report | IS | 2022-09-30 | Hardening document for POS will be provided by Q3-2022
15 | IT Control Environment: Access management policy and password history and failed login attempts are not documented | PwC Audit | ML | IS | 2022-09-30 | These two points will be incorporated in the Policy and same will be implemented in across UBL assets. Timeline will be Q3-2022
16 | Cyber Security Controls: Weaknesses in organogram of IS department | PwC Audit | ML | IS | 2022-06-30 | We will provide updated and sign off organogram of Info Sec Department by Q2-2022.
17 | Cyber Security Controls: Weaknesses identified in risk assessment | PwC Audit | ML | IS | 2022-12-31 | IS has started the comprehensive risk assessment of critical applications. Evidence will be shared in separate email
18 | Cyber Security Controls: Weaknesses found in Security Information and Event Management (SIEM) | PwC Audit | ML | IS | 2022-06-30 | It will be integrated with SIEM by Q2-2022.
19 | Cyber Security Controls: Weaknesses identified in asset classification | PwC Audit | ML | IS | 2022-12-31 | IS will performed the asset classification will be completed for above mention applications by Q4-2022.
20 | Cyber Security Controls: Weaknesses identified in incident response plan | PwC Audit | ML | IS | 2022-12-31 | Evidence shall be shared separately, further this shall be updated by Q4-2022
21 | Cyber Security Controls: Weaknesses identified in baseline configuration procedure | PwC Audit | ML | IS | 2022-09-30 | The review will be performed on above applications and will shared results by Q3-2022.
.

## Sheet1 (hidden)
Status | Count of Status
Closed | 4
In-progress | 8
To be Started | 2
Grand Total | 14

## Internal Audit
Year | Branch / Unit | Brief Detail of Exception | Management Response | Revised Target Date | Status | Risk | International / Domestic | Tagged
2024 | Information Security (IS Governance, VAPT and SOC) | Security policies are not reviewed annually, with last review conducted over 2 years ago. | Management agrees and will establish an annual policy review calendar with assigned owners. | Q2-2025 | Closed | Medium | International | IS
2024 | Information Security (IS Governance, VAPT and SOC) | SOC monitoring does not cover all critical systems, including certain cloud-hosted applications. | Management will onboard remaining systems into SOC monitoring within the next quarter. | Q2-2025 | open | High | International | IS
2024 | Information Security (IS Governance, VAPT and SOC) | VAPT exercises are conducted irregularly and not aligned with risk-based prioritization. | A risk-based VAPT schedule will be implemented starting next fiscal year. | Q1-2025 | Closed | Medium | International | IS
2024 | Vulnerability Management | Critical vulnerabilities are not remediated within defined SLA timelines. | A tracking dashboard will be implemented to monitor SLA compliance. | Q4-2024 | Closed | High | Domestic | IS
2024 | Vulnerability Management | Lack of centralized inventory of assets for vulnerability scanning. | Asset inventory tool implementation is in progress. | Q4-2024 | Closed | High | Domestic | IS
2024 | Vulnerability Management | Patch management process is partially manual, leading to delays. | Automation tools are being evaluated to streamline patching. | Q4-2024 | Closed | Medium | Domestic | IS
2019 | Cyber Security Management | Incident response plan is outdated and not tested through drills. | Plan will be updated and annual simulation exercises will be conducted. | Q2 2020 | Closed | High | Domestic | IS
2019 | Cyber Security Management | Security awareness training is not mandatory for all employees. | Mandatory training rollout is planned for all staff within 6 months. | Q2 2020 | Closed | Medium | Domestic | IS
2019 | Cyber Security Management | Lack of defined KPIs to measure cybersecurity effectiveness. | KPIs will be defined and tracked quarterly. | Q4 2020 | Closed | Low | Domestic | IS
2021 | Information Security Governance | Roles and responsibilities for information security are not clearly defined. | RACI matrix will be developed and communicated across departments. | Q2 2022 | Closed | Medium | Domestic | IS
2021 | Information Security Governance | No formal risk appetite statement for information security risks. | Risk appetite statement will be defined and approved by the board. | Q2 2022 | Closed | Medium | Domestic | IS
2021 | Information Security Governance | Information security steering committee meetings are not conducted regularly. | Quarterly meetings will be scheduled and documented going forward. | Q3 2021 | Closed | Low | Domestic | IS
2021 | Identity and Access Management (IAM) | User access reviews are not performed periodically for critical systems. | Quarterly access review process will be implemented. | Q3 2021 | Closed | High | Domestic | IS
2021 | Identity and Access Management (IAM) | Shared accounts are being used without proper monitoring. | Shared accounts will be eliminated or strictly controlled with monitoring. | Q2 2021 | Closed | High | Domestic | IS
2021 | Identity and Access Management (IAM) | Password policy does not enforce strong complexity requirements. | Password policy will be updated in line with best practices. | Q2 2022 | Closed | Medium | Domestic | IS
2021 | Identity and Access Management (IAM) | Delayed de-provisioning of user access after employee exit. | HR and IT integration will be enhanced for timely de-provisioning. | Q2 2022 | Closed | High | Domestic | IS
2024 | Application Security, Vulnerability Assessment and Penetration Testing Audit | Secure coding practices are not consistently followed across development teams. | Secure coding training will be provided and enforced via code reviews. | Q1-2025 | Closed | High | International | IS
2024 | Application Security, Vulnerability Assessment and Penetration Testing Audit | Penetration testing is not conducted before production releases. | Mandatory pre-release penetration testing will be enforced. | Q1-2025 | Closed | High | International | IS
2024 | Application Security, Vulnerability Assessment and Penetration Testing Audit | Lack of automated security testing in CI/CD pipeline. | Security tools will be integrated into CI/CD pipeline within 3 months. | Q2-2025 | Closed | Medium | International | IS
2024 | Application Security, Vulnerability Assessment and Penetration Testing Audit | Identified vulnerabilities are not tracked to closure. | A centralized tracking mechanism will be implemented. | Q2-2025 | Open | High | International | IS

## ML Int'l
Point No. | Year | Title | Observation | Recommendation | Rating | Owner/Action | Management Response - Sep'22 | Status
2.5 | 2019 | Absence of Review of Logs | System and application logs are generated but not periodically reviewed to identify suspicious activities or anomalies. | Implement a formal log review process with defined frequency, responsibilities, and escalation procedures. | High | IS | Management agrees and will implement automated log monitoring with weekly review reports. | Closed
2.5 | 2020 | Absence of review of logs for privileged users | Activities performed by privileged users are not logged or reviewed, increasing the risk of undetected misuse. | Enable logging for all privileged accounts and perform regular independent reviews of such logs. | High | IS | Privileged user monitoring tools will be deployed and monthly reviews will be initiated. | Closed
3.4 | 2021 | Information Security Organogram not approved | The information security organizational structure exists but has not been formally approved by senior management. | Obtain formal approval of the InfoSec organogram and communicate roles and responsibilities across the organization. | Medium | IS | The organogram will be presented for approval in the next governance committee meeting. | Closed
3.5 | 2021 | Inadequate periodic risk assessments process | Risk assessments are conducted on an ad-hoc basis without a defined methodology or schedule. | Establish a formal risk assessment framework with periodic assessments and documented outcomes. | High | IS | A risk assessment framework aligned with industry standards will be implemented annually. | Closed
3.7 | 2021 | Inappropriate classification of Information Assets | Information assets are not classified based on sensitivity and criticality, leading to inconsistent protection measures. | Develop and enforce an information classification policy with defined categories and handling procedures. | High | IS | Information classification guidelines will be developed and rolled out organization-wide. | Closed
3.8 | 2021 | Inappropriate incident response plan in place | The incident response plan is outdated and does not cover emerging cyber threats or define clear escalation paths. | Update the incident response plan and conduct periodic testing through simulations or drills. | High | IS | The plan will be updated and tabletop exercises will be conducted semi-annually. | Closed
3.9 | 2021 | Lack of periodic assessment of Baseline Security document | Baseline security standards are defined but not reviewed or updated regularly to reflect evolving threats. | Establish a periodic review process to update baseline security standards in line with industry best practices. | Medium | IS | Baseline documents will be reviewed annually and updated as required. | Closed
3.1 | 2021 | Inadequate procedure over data loss prevention | There is no formalized process or tool implemented for monitoring and preventing data leakage. | Implement a Data Loss Prevention (DLP) solution and define procedures for monitoring and incident handling. | High | IS | A DLP solution is under evaluation and procedures will be documented post-implementation. | Closed IS part has been closed
3.11 | 2021 | Absence of Vulnerability Assessment | No regular vulnerability assessments are conducted on internal systems and infrastructure. | Conduct periodic vulnerability assessments and track remediation of identified issues. | High | IS | Quarterly vulnerability assessments will be initiated with tracking dashboards. | Closed
3.12 | 2021 | Absence of formal documented IT Policies and Procedures | IT policies and procedures are either undocumented or not formally approved, leading to inconsistent practices. | Develop, document, and approve IT policies and ensure they are communicated across the organization. | High | IS | A policy development initiative is underway and will be completed within 6 months. | Closed
4 | 2023 | Absence of Vulnerability Assessment / Penetration Testing | Neither vulnerability assessments nor penetration testing exercises are conducted for critical systems and applications. | Establish a VAPT program including regular internal and external testing with remediation tracking. | High | IS | External consultants will be engaged to conduct annual penetration testing and internal scans. | Closed

## ML Domestic
Point No. | Year | Title | Observation | Recommendation | Rating | Owner | Management Response - Sep'22 | Status | Revised Target Date
10.9 | 2021 | Weaknesses identified in risk assessment: Risk Medium | The risk assessment process does not consistently consider all critical assets and lacks proper documentation of risk treatment plans. | Enhance the risk assessment methodology to ensure comprehensive asset coverage and formal documentation of risk mitigation actions. | Medium | IS | Management will update the risk assessment framework and ensure all risks are documented with treatment plans. | Closed | Q2-2023
10.8 | 2021 | Weaknesses in organogram of IS | The Information Security organogram does not clearly define reporting lines and segregation of duties, leading to potential conflicts of interest. | Revise the organogram to clearly define roles, responsibilities, and reporting structure in line with governance best practices. | Medium | IS | The organogram will be restructured and approved by senior management. | Closed | 2022
10.10 | 2021 | Weaknesses found in Security Information and Event Management (SIEM) | SIEM implementation lacks proper use case coverage and correlation rules, resulting in ineffective detection of security incidents. | Enhance SIEM configuration by defining relevant use cases, correlation rules, and regular tuning. | High | IS | SIEM use cases will be reviewed and optimized with assistance from external experts. | Re-taggeing Requested, Closed further marked to IS
10.1 | 2021 | Access management policy and password history and failed login attempts | Password policy does not enforce history checks and account lockout after multiple failed login attempts. | Strengthen password policy by enforcing password history, complexity, and account lockout thresholds. | High | IS | Password policy will be updated and implemented across all systems. | Closed | Q1-2023
10.11 | 2021 | Weaknesses identified in asset classification | Asset classification is inconsistently applied, and some critical assets are either misclassified or not classified at all. | Conduct a comprehensive asset classification exercise and enforce compliance with classification guidelines. | High | IS | A reclassification exercise will be conducted and monitored periodically. | Closed | Q2-2023
10.12 | 2021 | Inappropriate incident response plan in place | Incident response procedures lack clarity on roles, communication protocols, and recovery steps. | Update the incident response plan to include detailed roles, escalation matrix, and recovery procedures, followed by testing. | High | IS | The incident response plan will be revised and tested through simulation exercises. | Closed
10.13 | 2021 | Weaknesses identified in baseline configuration procedure | Baseline configuration standards are not enforced consistently across systems, leading to configuration drift. | Implement automated configuration management tools to enforce and monitor baseline compliance. | Medium | IS | Tools for configuration management will be evaluated and deployed. | Closed
10.14 | 2021 | Weaknesses Identified in data loss prevention procedure | Existing DLP procedures are not supported by adequate monitoring tools and lack defined incident handling workflows. | Strengthen DLP processes by implementing tools and defining clear workflows for incident detection and response. | High | IS | DLP tools will be implemented and procedures updated accordingly. | Closed
10.15 | 2021 | Weaknesses identified in vulnerability assessment procedure | Vulnerability assessment procedures lack defined scope, frequency, and remediation tracking mechanisms. | Define a formal vulnerability management procedure with clear scope, timelines, and tracking of remediation. | High | IS | A formal procedure will be documented and implemented with tracking dashboards. | Closed
3 | 2023 | Incomplete Vulnerability Assessment & Penetration Testing (VAPT) Coverage | VAPT activities do not cover all critical applications, systems, and network components. | Expand VAPT scope to include all critical assets and ensure periodic testing. | High | IS | Management will ensure complete coverage in future VAPT cycles and maintain an asset inventory. | Closed | 2024-05-01

## SBP
S. No | Report Name | CG Ref. No. | SBP Observation | Pertain to | Group | Groups Revised | Management Response | Target Date | Initial Timeline | Status 1 | IA Comments (14-Sep-2022)
| CYBERSECURITY AS OF 31-12-2024 | Board of Directors and Senior Management 2.1 | Inadequate Cybersecurity Governance Framework: The organization lacks a formally approved cybersecurity governance framework aligned with regulatory requirements, resulting in inconsistent security practices. Recommendation: Develop and obtain board approval for a comprehensive cybersecurity governance framework aligned with applicable regulations and standards. | IT / IS |  |  | Management agrees and will develop a formal cybersecurity governance framework aligned with regulatory guidelines within the next two quarters. | 2025-08-31 |  | Open
| CYBERSECURITY AS OF 31-12-2024 | 2.2 | Absence of Regulatory Compliance Monitoring Mechanism: There is no structured process to track compliance with regulatory requirements, increasing the risk of non-compliance. Recommendation: Implement a compliance monitoring framework with periodic reporting to senior management. | IS/ IT |  |  | A compliance tracking mechanism will be established, and quarterly compliance reports will be presented to management. | 2025-08-31 |  | Open
| CYBERSECURITY AS OF 31-12-2024 | 2.6 | Weak Third-Party Risk Management Controls: Due diligence and ongoing monitoring of third-party vendors are not consistently performed. Recommendation: Establish a formal third-party risk management program including risk assessments and periodic reviews. | IT / IS |  |  | Management will enhance vendor risk assessment procedures and implement periodic monitoring controls. | 2025-08-31 |  | Open
| CYBERSECURITY AS OF 31-12-2024 | 1.4 | Lack of Data Protection and Privacy Controls: Sensitive data is not adequately protected or classified in accordance with regulatory expectations. Recommendation: Implement data classification, encryption, and privacy controls in line with regulatory requirements. | IT/IS |  |  | Data classification and encryption initiatives are currently underway and will be completed within six months. | Q4-2025 |  | Open
| CYBERSECURITY AS OF 31-12-2024 | 1.6 | Ineffective Security Incident Reporting to Regulators: There is no defined process for timely reporting of cybersecurity incidents to regulators. Recommendation: Develop and implement an incident reporting protocol aligned with regulatory timelines. | IT / IS |  |  | Incident reporting procedures will be formalized and integrated into the incident response plan. | 2025-09-30 |  | Open
| CYBERSECURITY AS OF 31-12-2024 | 1.7 | Inadequate Logging and Monitoring Controls: Logs are not centrally monitored, limiting the organization’s ability to detect suspicious activities. Recommendation: Implement centralized logging and continuous monitoring through SIEM solutions. | IT/IS |  | Timeline for compliance will be extended from Q2 2025 to Q4 2025. | A SIEM solution will be enhanced to ensure centralized logging and real-time monitoring. |  |  | Open
| CYBERSECURITY AS OF 31-12-2024 | 1.1 | Deficiencies in Identity and Access Management Controls: User access provisioning and de-provisioning processes are not consistently enforced. Recommendation: Strengthen IAM processes including periodic access reviews and automation of provisioning. | IT / IS / IAM |  |  | IAM processes will be automated and quarterly access reviews will be enforced. | 2025-06-30 |  | Closed
| CYBERSECURITY AS OF 31-12-2024 | 1.13 | Lack of Periodic Cybersecurity Awareness Training: Employees are not regularly trained on cybersecurity risks, increasing susceptibility to attacks. Recommendation: Conduct mandatory periodic cybersecurity awareness training programs. | IT / IS |  |  | A mandatory training program will be launched for all employees annually. | 2025-09-30 |  | Open
| CYBERSECURITY AS OF 31-12-2024 | 1.14 | Absence of Business Continuity and Disaster Recovery Testing: BCP and DR plans are documented but not periodically tested. Recommendation: Conduct regular BCP/DR testing and document outcomes for improvement. | IT / IS |  |  | Management will conduct annual DR drills and document lessons learned. | 2025-07-31 |  | Open
| SBP On-site Assessment as of 31-01-2025 | 1.15 | Weak Network Security Controls: Network segmentation and firewall rules are not regularly reviewed, increasing exposure to threats. Recommendation: Strengthen network security architecture and conduct periodic reviews. | IT / IS |  |  | Firewall and network segmentation reviews will be conducted semi-annually. | Q1-2026 |  | open
| SBP On-site Assessment as of 31-01-2025 | 5 | Inadequate Patch Management Process: Security patches are not applied within defined timelines, leaving systems vulnerable. Recommendation: Implement an automated patch management solution with defined SLAs. | IS |  |  | Patch management tools are being deployed to ensure timely updates. | 2025-12-31 | In progress | Closed
| SBP On-site Assessment as of 31-01-2025 | 4.1 | Insufficient Vulnerability Management Practices: Identified vulnerabilities are not tracked to closure, and remediation timelines are not enforced. Recommendation: Implement a vulnerability tracking system with defined SLAs and reporting. | IS |  |  | A centralized vulnerability tracking dashboard will be implemented. | 2025-12-31 |  | Open
| SBP On-site Assessment as of 31-01-2025 | 4.2 | Lack of Secure Configuration Standards: Systems are not configured according to secure baseline standards, increasing risk exposure. Recommendation: Develop and enforce secure configuration baselines across all systems. | IT / IS |  |  | Baseline configuration standards will be defined and enforced using automated tools. | 2025-12-31 |  | Open
| SBP On-site Assessment as of 31-01-2025 | 4.3 | Inadequate Audit Trail Retention: Log retention periods do not meet regulatory requirements, limiting forensic capabilities. Recommendation: Define and enforce log retention policies aligned with regulatory expectations. | IS |  |  | Log retention policies will be updated to meet regulatory requirements. | 2025-12-31 |  | Open
| SBP On-site Assessment as of 31-01-2025 | 4.4 | Weak Change Management Controls in IT Systems: Changes to critical systems are not consistently documented or approved. Recommendation: Strengthen change management processes with proper approvals and audit trails. | IS |  |  | Change management procedures will be reinforced, and compliance will be monitored regularly. | 2025-12-31 |  | Closed

## Dashboard
IS Audit | Total | Closed | Open | Closed as of Q4-2022 | Closed as of Q1-2023 | Closed as of Q2-2023 | Closed as of Q3-2023 | Closed as of Q4-2023 | Closed as of Jan-2024 | Closed as of May-2024 | Closed as of June-2024 | Closed as of Q3-2024 | Closed as of Q4-2024 | Closed as of Q1-2025 | Closed as of Q1-2025 | Closed as of Q2-2025 | Closed as of Q4-2025 | Closed as of Q1-2026 | Work-in-progress- IS | Under Validation with IA/Compliance | Referred to Business | Severity / priority
Overall compliance and progress | [21 empty] | H | M | L
Information Security (IS Governance, VAPT and SOC) | 3 | 2 | 1 | 0 | 0 | 1 |  | 2 |  | 1 | [8 empty] | 0 | 1 | 0 | 0 | 0 | 0
Vulnerability Management | 3 | 3 |  | 1 | 0 | 0 |  |  |  |  | 1 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Cyber Security Management | 3 | 3 |  | 0 | 5 | 1 |  |  |  | 1 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Information Security Governance | 3 | 3 | [8 empty] | 1 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Identity and Access Management (IAM) | 4 | 4 |  | 5 | 2 | 12 | 2 | 1 | 2 | 1 | 2 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Application Security, Vulnerability Assessment and Penetration Testing Audit | 4 | 3 | 1 | 1 | 1 | 7 |  |  |  | 2 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
ML Int'l | 11 | 11 |  | 4 | 3 | 2 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
ML Domestic | 10 | 10 |  | 6 | 2 | 2 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
SBP | 15 | 3 | 12 | [7 empty] | 1 | [7 empty] | 9 | 3 | 0 | 0 | 0 | 0
Grand Total | 56 | 42 | 14 | 17 | 13 | 25 | 2 | 3 | 2 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 0 | 0 | 0 | 0