## Template
PA Milestone | PCI DSS v4.0.1 Requirement | Requirement Title / Control Objective | Testing Procedure Reference | In Scope | Applicability Rationale | Business Area / Process | System / Asset / CDE Component | Current Implementation Status | Gap Description | Remediation Action | Action Owner | Accountable Manager | Target Completion Date | Actual Completion Date | Priority | Risk Rating | Dependency / Blocker | Evidence Required | Evidence Location | Validation Method | Validated By | Validation Date | Residual Risk / Exception Reference | Compensating Control Reference | Assessor / QSA Comments | Last Updated | Overall RAG Status
[EXAMPLE: M1] | [EXAMPLE: 1.2.1] | [EXAMPLE: Network security controls are configured and maintained] | [EXAMPLE: 1.2.1.a] | [EXAMPLE: Yes] | [EXAMPLE: Applies because firewalls segment the CDE from corporate networks] | [EXAMPLE: Infrastructure Operations] | [EXAMPLE: CDE firewall cluster FW-CDE-01] | [EXAMPLE: In Progress] | [EXAMPLE: Firewall rule review procedure is not yet formally documented] | [EXAMPLE: Create and approve firewall rule review procedure and link it to change management] | [EXAMPLE: Network Security Lead] | [EXAMPLE: Head of Infrastructure] | [EXAMPLE: 2026-03-31] | [EXAMPLE: ] | [EXAMPLE: High] | [EXAMPLE: High] | [EXAMPLE: Awaiting CAB approval] | [EXAMPLE: Approved procedure, firewall rule review record, change tickets] | [EXAMPLE: GRC-EVID-PCI-001] | [EXAMPLE: Document Review] | [EXAMPLE: ] | [EXAMPLE: ] | [EXAMPLE: N/A] | [EXAMPLE: N/A] | [EXAMPLE: QSA to review after procedure approval] | [EXAMPLE: 2026-02-15] | [EXAMPLE: Amber]
[EXAMPLE: M3] | [EXAMPLE: 8.3.6] | [EXAMPLE: Minimum password/passphrase complexity is configured] | [EXAMPLE: 8.3.6.b] | [EXAMPLE: Yes] | [EXAMPLE: Applies to administrator authentication for systems in the CDE] | [EXAMPLE: Identity and Access Management] | [EXAMPLE: CDE Active Directory domain] | [EXAMPLE: Implemented Not Validated] | [EXAMPLE: Configuration changed but evidence has not yet been independently validated] | [EXAMPLE: Validate password policy settings and retain configuration export] | [EXAMPLE: IAM Engineer] | [EXAMPLE: IAM Manager] | [EXAMPLE: 2026-04-15] | [EXAMPLE: 2026-04-10] | [EXAMPLE: Medium] | [EXAMPLE: Medium] | [EXAMPLE: None] | [EXAMPLE: Password policy export, screenshot, validation ticket] | [EXAMPLE: SharePoint/PCI/2026/Req-8.3.6] | [EXAMPLE: Configuration Review] | [EXAMPLE: Internal Security Assessor] | [EXAMPLE: 2026-04-12] | [EXAMPLE: N/A] | [EXAMPLE: N/A] | [EXAMPLE: Evidence acceptable subject to sample testing] | [EXAMPLE: 2026-04-12] | [EXAMPLE: Green]

## Column Guidance
Column | What to enter
PA Milestone | Enter the Prioritized Approach milestone number or grouping used by the PCI DSS v4.0.1 Prioritized Approach Tool, for example M1, M2, M3, M4, M5, or M6.
PCI DSS v4.0.1 Requirement | Enter the exact PCI DSS v4.0.1 requirement reference being tracked, for example 1.2.1, 3.5.1, 8.3.6, or 12.10.1.
Requirement Title / Control Objective | Enter a short description of the PCI DSS requirement or intended control outcome in plain language.
Testing Procedure Reference | Enter the related PCI DSS v4.0.1 testing procedure reference where applicable, for example 1.2.1.a or 8.3.6.b; enter N/A if not applicable.
In Scope | Enter Yes or No to indicate whether the requirement applies to the organisation’s PCI DSS assessment scope.
Applicability Rationale | Explain why the requirement is applicable or not applicable, referencing the cardholder data environment, payment channel, system type, process, or documented scoping decision.
Business Area / Process | Enter the business unit, team, or payment process responsible for or affected by the requirement.
System / Asset / CDE Component | Enter the system, application, network segment, database, service provider, or CDE component affected; use asset inventory names where available.
Current Implementation Status | Enter one allowed value: Not Started, In Progress, Implemented Not Validated, Validated, Not Applicable, or Deferred.
Gap Description | Describe the current gap preventing compliance; enter None if the requirement is already implemented and validated.
Remediation Action | Describe the specific action needed to meet the PCI DSS requirement, including the expected deliverable or control change.
Action Owner | Enter the named person or role responsible for completing the remediation action.
Accountable Manager | Enter the manager or control owner accountable for ensuring the action is completed and sustained.
Target Completion Date | Enter the planned completion date in YYYY-MM-DD format.
Actual Completion Date | Enter the actual date the remediation was completed in YYYY-MM-DD format; leave blank until complete.
Priority | Enter one allowed value: Critical, High, Medium, or Low, based on compliance impact, risk, and dependency sequencing.
Risk Rating | Enter one allowed value: Critical, High, Medium, Low, or Informational, based on risk to cardholder data if the gap remains unresolved.
Dependency / Blocker | Record any dependency, blocker, project, vendor, approval, technology change, or prerequisite affecting completion; enter None if there are no blockers.
Evidence Required | List the evidence expected to prove implementation, such as configuration screenshots, policy, procedure, system report, ticket, log sample, scan result, diagram, or interview record.
Evidence Location | Enter the repository path, GRC record ID, ticket link, document link, or evidence folder location where supporting evidence is stored.
Validation Method | Enter how completion will be verified, for example Document Review, Configuration Review, Interview, Observation, Sampling, Technical Test, or QSA Review.
Validated By | Enter the name or role of the person who validated the requirement status; leave blank until validation occurs.
Validation Date | Enter the date validation was performed in YYYY-MM-DD format; leave blank until validation occurs.
Residual Risk / Exception Reference | Enter the approved risk acceptance, exception, or deferral reference if compliance is not fully achieved; enter N/A if no residual risk or exception applies.
Compensating Control Reference | Enter the compensating control worksheet or control reference if a compensating control is used; enter N/A if not used.
Assessor / QSA Comments | Enter comments, findings, clarification requests, or acceptance notes from the internal assessor, ISA, or QSA.
Last Updated | Enter the date this row was last updated in YYYY-MM-DD format.
Overall RAG Status | Enter one allowed value: Red, Amber, Green, or Grey, where Red means overdue or major gap, Amber means in progress or at risk, Green means complete and validated, and Grey means not applicable or deferred.

## Notes
Maintenance
Owned by the PCI Compliance Manager or GRC Lead, with action updates provided by control owners and remediation owners at least weekly during the compliance programme and before each assessment checkpoint. Source data should be drawn from the PCI DSS v4.0.1 Prioritized Approach Tool, GRC platform, remediation tracker, asset inventory, ticketing system, evidence repository, and assessor/QSA review notes.