## Template
NC ID | Date Identified | Identified By | Source of Nonconformity | ISO 41001 Clause / FMS Requirement | FM Process / Service Area | Location / Site | Nonconformity Description | Objective Evidence | Immediate Correction / Containment Taken | Consequences / Impact | Severity | Responsible Owner | Root Cause Analysis Method | Root Cause | Similar or Potential Nonconformities Assessed | Corrective Action Required | Corrective Action Plan | Action Owner | Target Completion Date | Actual Completion Date | Implementation Status | Effectiveness Review Method | Effectiveness Review Date | Effectiveness Review Result | Further Action Required | Risks / Opportunities Updated | FMS Documentation / Process Changes Required | Evidence Reference / Link | Closure Approval By | Closure Date | Record Status
[EXAMPLE: NC-FM-2026-001] | [EXAMPLE: 2026-02-14] | [EXAMPLE: J. Smith, Internal Auditor] | [EXAMPLE: Internal Audit] | [EXAMPLE: ISO 41001:2018 Cl. 8.1; FM-PR-07 Planned Maintenance Procedure] | [EXAMPLE: Planned maintenance] | [EXAMPLE: HQ Building, Level 3 AHU Plantroom] | [EXAMPLE: Preventive maintenance tasks for AHU-03 were not completed within the planned monthly interval required by procedure FM-PR-07.] | [EXAMPLE: Audit sample WO-45821 and maintenance schedule extract dated 2026-02-10] | [EXAMPLE: Overdue maintenance completed on 2026-02-15 and asset condition checked with no immediate safety issue found.] | [EXAMPLE: Potential reduced equipment reliability and SLA breach for planned maintenance completion.] | [EXAMPLE: Medium] | [EXAMPLE: Facilities Maintenance Manager] | [EXAMPLE: 5 Whys] | [EXAMPLE: Maintenance schedule changes were not reviewed after contractor resource changes, causing tasks to be assigned to an inactive technician queue.] | [EXAMPLE: Yes - checked all AHU monthly PMs for HQ and two additional overdue tasks were identified.] | [EXAMPLE: Yes] | [EXAMPLE: Update scheduling rules, remove inactive technician queues, add weekly exception report review, and brief maintenance planners.] | [EXAMPLE: Maintenance Planning Lead] | [EXAMPLE: 2026-03-10] | [EXAMPLE: 2026-03-08] | [EXAMPLE: Implemented Pending Effectiveness Review] | [EXAMPLE: Review next two weekly overdue PM exception reports and sample five completed PM work orders.] | [EXAMPLE: 2026-03-25] | [EXAMPLE: Effective - no overdue AHU PMs identified in two reporting cycles.] | [EXAMPLE: None] | [EXAMPLE: Yes - FM risk register RR-FM-012 updated for contractor resource dependency.] | [EXAMPLE: FM-PR-07 and planner work instruction WI-FM-04 updated.] | [EXAMPLE: CMMS WO-45821; Exception Report ER-2026-011; Document change DC-2026-006] | [EXAMPLE: Head of Facilities Operations] | [EXAMPLE: 2026-03-26] | [EXAMPLE: Closed]

## Column Guidance
Column | What to enter
NC ID | Enter a unique identifier for the nonconformity, using a consistent format such as NC-FM-YYYY-###.
Date Identified | Enter the date the nonconformity was first identified in YYYY-MM-DD format.
Identified By | Enter the name and role of the person who identified or reported the nonconformity.
Source of Nonconformity | Select or enter the source, such as Internal Audit, External Audit, Management Review, Client Complaint, Service Failure, KPI Monitoring, Supplier Issue, Incident, Inspection, Employee Report, or Other.
ISO 41001 Clause / FMS Requirement | Enter the applicable ISO 41001:2018 clause, contractual requirement, internal procedure, SLA, policy, or FM requirement that was not met.
FM Process / Service Area | Enter the affected facilities management process or service area, such as maintenance, cleaning, security, catering, utilities, space management, helpdesk, contractor management, asset management, or H&S interface.
Location / Site | Enter the site, building, floor, asset location, client location, or operational area affected by the nonconformity.
Nonconformity Description | Describe clearly what failed to conform, including what happened, where, when, and the requirement not met; do not include root cause unless already verified.
Objective Evidence | Enter the evidence supporting the nonconformity, such as audit finding, work order number, inspection record, photo reference, complaint ID, KPI report, log entry, or document reference.
Immediate Correction / Containment Taken | Record immediate action taken to control, correct, contain, or mitigate the nonconformity and its consequences, including date if applicable.
Consequences / Impact | Describe the actual or potential impact on FM service delivery, users, client obligations, safety, compliance, assets, business continuity, environment, cost, or reputation.
Severity | Enter the assessed severity using agreed values such as Low, Medium, High, or Critical, based on organisational criteria.
Responsible Owner | Enter the manager accountable for ensuring the nonconformity is investigated and resolved.
Root Cause Analysis Method | Enter the method used to determine cause, such as 5 Whys, Fishbone, Fault Tree, Pareto, Incident Investigation, Process Review, or Not Required with justification.
Root Cause | Enter the verified underlying cause or causes of the nonconformity; avoid restating the symptom.
Similar or Potential Nonconformities Assessed | Record whether similar nonconformities exist or could occur elsewhere, including areas checked; use Yes, No, or Not Applicable with brief explanation.
Corrective Action Required | Enter Yes or No; use Yes where action is needed to eliminate the root cause and prevent recurrence or occurrence elsewhere.
Corrective Action Plan | Describe the planned corrective action(s) to eliminate the root cause, including enough detail to verify implementation.
Action Owner | Enter the person or role responsible for completing the corrective action.
Target Completion Date | Enter the planned completion date for the corrective action in YYYY-MM-DD format.
Actual Completion Date | Enter the date the corrective action was fully implemented in YYYY-MM-DD format; leave blank until complete.
Implementation Status | Enter the current status using Not Started, In Progress, Implemented Pending Effectiveness Review, Closed, Overdue, or Cancelled.
Effectiveness Review Method | Describe how effectiveness will be verified, such as repeat audit, KPI trend review, inspection, sample check, customer feedback, work order review, or observation.
Effectiveness Review Date | Enter the date the effectiveness review was or will be performed in YYYY-MM-DD format.
Effectiveness Review Result | Enter the outcome of the effectiveness review using Effective, Not Effective, Partially Effective, or Pending, with a brief rationale.
Further Action Required | Enter any additional corrective action required if the original action was not effective, or enter None.
Risks / Opportunities Updated | Enter Yes, No, or Not Applicable and reference the risk/opportunity register entry updated where relevant.
FMS Documentation / Process Changes Required | Enter any required updates to FMS documents, procedures, work instructions, training, contracts, SLAs, process maps, or controls; enter None if no change is required.
Evidence Reference / Link | Enter document IDs, system links, folder paths, work order references, audit report numbers, photos, approvals, or other records proving actions and results.
Closure Approval By | Enter the name and role of the authorised person approving closure, independent of the action owner where practicable.
Closure Date | Enter the date the nonconformity and corrective action were formally closed in YYYY-MM-DD format.
Record Status | Enter Open, Closed, Reopened, or Archived.

## Notes
Maintenance
The FMS Manager or designated Quality/FM Compliance Manager owns this register and updates it whenever a nonconformity is identified, with formal review at least monthly and before management review. Source data is drawn from audits, inspections, FM helpdesk/CMMS, complaints, KPI reports, incident records, supplier performance records, and management review outputs.