## Template
Improvement ID | Date Raised | Raised By | Improvement Source | Source Reference | ISO 41001 Clause / FM Process | Facility / Site / Service Area | Interested Party / Customer Affected | Current Issue or Opportunity Statement | Improvement Category | Intended Improvement Objective | Alignment to FM Policy / FM Objectives | Baseline Performance / Current State | Target Outcome / Success Measure | Risk or Opportunity Rating | Priority | Proposed Improvement Action | Action Owner | Approver / Sponsor | Resources or Budget Required | Planned Start Date | Target Completion Date | Status | Progress / Update Notes | Related Corrective Action ID | Evidence / Record Location | Actual Completion Date | Effectiveness Review Required | Effectiveness Review Date | Effectiveness Review Result | Benefit Realised | Lessons Learned / Standardisation Action | Closure Approval | Closure Date
[EXAMPLE: CI-2026-001] | [EXAMPLE: 2026-01-15] | [EXAMPLE: Helpdesk Manager] | [EXAMPLE: KPI Trend] | [EXAMPLE: KPI-DASH-FM-2025-Q4] | [EXAMPLE: Cl. 9.1 Performance Evaluation / Helpdesk] | [EXAMPLE: Head Office / FM Helpdesk] | [EXAMPLE: Building occupants and department coordinators] | [EXAMPLE: Average response time for priority 2 work orders exceeded the agreed service level for three consecutive months.] | [EXAMPLE: Improve FM Service] | [EXAMPLE: Reduce priority 2 response time to within agreed SLA and improve user satisfaction.] | [EXAMPLE: FM Objective 2 - Improve responsiveness of workplace services] | [EXAMPLE: Average P2 response time 9.5 hours, Oct-Dec 2025, target SLA 6 hours] | [EXAMPLE: Average P2 response time <=6 hours for two consecutive months] | [EXAMPLE: High] | [EXAMPLE: High] | [EXAMPLE: Review triage rules, rebalance technician allocation, and introduce daily queue monitoring.] | [EXAMPLE: Helpdesk Manager] | [EXAMPLE: FM Operations Lead] | [EXAMPLE: Internal labour; no additional budget expected] | [EXAMPLE: 2026-02-01] | [EXAMPLE: 2026-03-31] | [EXAMPLE: In Progress] | [EXAMPLE: 2026-02-15 - Queue dashboard configured and pilot triage process started.] | [EXAMPLE: N/A] | [EXAMPLE: SharePoint/FM/ContinualImprovement/CI-2026-001] | [EXAMPLE: ] | [EXAMPLE: Yes] | [EXAMPLE: 2026-05-01] | [EXAMPLE: Too Early to Confirm] | [EXAMPLE: Pending measurement after two full months of operation] | [EXAMPLE: Pending; update helpdesk procedure if effective] | [EXAMPLE: Pending FM Operations Lead approval] | [EXAMPLE: ]
[EXAMPLE: CI-2026-002] | [EXAMPLE: 2026-02-10] | [EXAMPLE: Facilities Compliance Coordinator] | [EXAMPLE: Internal Audit] | [EXAMPLE: IA-FM-2026-03-OBS-04] | [EXAMPLE: Cl. 8.1 Operations / Contractor Management] | [EXAMPLE: All managed sites] | [EXAMPLE: FM contractors and site users] | [EXAMPLE: Contractor induction records are held inconsistently across sites, making verification slow and increasing compliance risk.] | [EXAMPLE: Improve FMS Effectiveness] | [EXAMPLE: Standardise contractor induction record capture and improve availability of compliance evidence.] | [EXAMPLE: FM Policy commitment to safe, compliant and controlled service delivery] | [EXAMPLE: 62% of sampled contractor files had complete induction evidence in Jan 2026 audit sample] | [EXAMPLE: 95% complete induction evidence for active contractors by 2026-06-30] | [EXAMPLE: Medium] | [EXAMPLE: Medium] | [EXAMPLE: Implement a single electronic induction register and require upload before work authorisation.] | [EXAMPLE: Contractor Management Process Owner] | [EXAMPLE: Head of Facilities] | [EXAMPLE: Compliance system configuration; estimated GBP 2,500] | [EXAMPLE: 2026-03-01] | [EXAMPLE: 2026-05-31] | [EXAMPLE: Approved] | [EXAMPLE: 2026-02-20 - Sponsor approved system configuration and pilot site selected.] | [EXAMPLE: CA-2026-014] | [EXAMPLE: GRC System/CAPA/CA-2026-014 and Contractor Portal project folder] | [EXAMPLE: ] | [EXAMPLE: Yes] | [EXAMPLE: 2026-07-15] | [EXAMPLE: Too Early to Confirm] | [EXAMPLE: Pending post-implementation sample review] | [EXAMPLE: Pending; update contractor onboarding procedure and site manager training pack] | [EXAMPLE: Pending Head of Facilities approval] | [EXAMPLE: ]

## Column Guidance
Column | What to enter
Improvement ID | Enter a unique identifier for the improvement initiative, using a controlled format such as CI-YYYY-###.
Date Raised | Enter the date the improvement opportunity was formally logged, in YYYY-MM-DD format.
Raised By | Enter the name and role or function of the person who identified or submitted the improvement opportunity.
Improvement Source | Select the origin of the improvement from allowed values: Internal Audit, External Audit, Management Review, KPI Trend, Customer Feedback, Complaint, Risk Assessment, Incident, Nonconformity, Supplier Review, Staff Suggestion, Benchmarking, Regulatory Change, Technology / Innovation, Other.
Source Reference | Enter the reference number, report name, meeting minute ID, audit finding ID, KPI dashboard link, ticket number, or other traceable source reference.
ISO 41001 Clause / FM Process | Enter the relevant ISO 41001 clause where applicable and/or the FM process affected, for example Cl. 8.1 Operations, Cl. 9.1 Performance Evaluation, Maintenance, Cleaning, Space Management, Helpdesk, Security, Energy Management.
Facility / Site / Service Area | Enter the specific facility, site, building, region, department, asset group, or FM service area to which the improvement applies.
Interested Party / Customer Affected | Enter the customer, client, occupier group, internal department, regulator, supplier, user group, or other interested party affected by the improvement.
Current Issue or Opportunity Statement | Describe the current condition, gap, inefficiency, trend, risk, or opportunity in clear factual terms; avoid describing the solution only.
Improvement Category | Select the primary intent from allowed values: Improve FM Service, Improve FMS Effectiveness, Enhance Customer Satisfaction, Reduce Undesired Effect, Prevent Undesired Effect, Correct Undesired Effect, Improve Efficiency, Improve Compliance, Improve Sustainability, Other.
Intended Improvement Objective | State what the initiative is intended to achieve, written as a measurable improvement objective where possible.
Alignment to FM Policy / FM Objectives | Identify the relevant FM policy commitment, FM objective, performance target, customer requirement, or strategic business aim supported by the improvement.
Baseline Performance / Current State | Record the starting performance level or current state before action, including metric name, value, unit, and measurement period where applicable.
Target Outcome / Success Measure | Define the expected result and acceptance criteria, including KPI, target value, unit, threshold, or qualitative success condition.
Risk or Opportunity Rating | Enter the assessed significance using the organisation's risk method, for example Low, Medium, High, Critical, or a numeric score such as Likelihood x Impact.
Priority | Select the implementation priority from allowed values: Low, Medium, High, Urgent.
Proposed Improvement Action | Describe the planned action or initiative to implement the improvement, including key deliverables or change activities.
Action Owner | Enter the named person and role accountable for coordinating and delivering the improvement action.
Approver / Sponsor | Enter the manager, process owner, contract lead, FM director, or governance body approving resources and priority for the initiative.
Resources or Budget Required | Record required resources such as budget, labour, contractor support, tools, technology, training, or capital expenditure; include amount and currency where known.
Planned Start Date | Enter the planned commencement date for the improvement action, in YYYY-MM-DD format.
Target Completion Date | Enter the planned completion date for the improvement action, in YYYY-MM-DD format.
Status | Select the current lifecycle status from allowed values: Proposed, Approved, Not Started, In Progress, On Hold, Completed, Effectiveness Review Pending, Closed, Cancelled.
Progress / Update Notes | Enter dated progress notes, decisions, blockers, escalations, or changes to scope; each update should include date, author, and summary.
Related Corrective Action ID | Enter any linked corrective action, nonconformity, incident, risk treatment, audit finding, or CAPA reference; enter N/A if not applicable.
Evidence / Record Location | Enter the controlled document repository path, system link, ticket URL, project folder, report reference, or other evidence location proving implementation.
Actual Completion Date | Enter the date the improvement action was completed, in YYYY-MM-DD format; leave blank until completed.
Effectiveness Review Required | Select Yes or No to indicate whether post-implementation effectiveness must be verified.
Effectiveness Review Date | Enter the planned or actual date for checking whether the improvement achieved its intended outcome, in YYYY-MM-DD format.
Effectiveness Review Result | Record the result of the effectiveness check using allowed values: Effective, Partially Effective, Not Effective, Too Early to Confirm, Not Required; include brief rationale if needed.
Benefit Realised | Record the actual benefit achieved, including measured KPI change, cost saving, risk reduction, service improvement, customer satisfaction result, compliance improvement, or qualitative benefit.
Lessons Learned / Standardisation Action | Record any lessons learned and whether changes were embedded into procedures, training, specifications, contracts, checklists, asset plans, or monitoring arrangements.
Closure Approval | Enter the name, role, and approval decision of the person authorised to close the initiative after completion and effectiveness review.
Closure Date | Enter the date the improvement initiative was formally closed, in YYYY-MM-DD format.

## Notes
Maintenance
The FM Management System Manager owns this template, with updates made at least monthly and reviewed during management review for trends, overdue actions, and effectiveness of improvements. The register draws from the GRC/CAPA system, FM helpdesk or CAFM system, audit reports, KPI dashboards, customer feedback records, risk registers, and management review outputs.