## Cover
[Bank Name]
ENTERPRISE IT RISK REGISTER
Cyber, Technology & Operational Risk Inventory
Evidence ID: | EV-RSK-001
Document Type: | Risk Register
Classification: | CONFIDENTIAL — INTERNAL USE
Version: | 2.1
Issue Date: | 31-Mar-2026
Next Review: | 30-Sep-2026
Document Owner: | Chief Information Security Officer (CISO)
Approved By: | Board IT Committee
Retention Period: | 7 years
FRAMEWORKS SATISFIED BY THIS EVIDENCE
CBUAE Chapter 14 | Foundational — supports all clauses
SBP ETGRMF | 2.1 Risk Management; 2.8 Risk Appetite; 2.9 Threat Intelligence
SBP IB Regulations | 2.1 Governance; 2.1(e) Risk Assessment
ISO 27001:2022 | Clause 6.1.2 & 6.1.3; A.5.4 Mgmt Responsibility; A.5.7 Threat Intel
PCI-DSS v4.0.1 | Req 12.3 Risk Analysis; Req 12.3.1 Targeted Risk Analysis
PURPOSE & SCOPE
This Enterprise IT Risk Register captures all identified cyber, technology and operational technology risks across the Bank. It is reviewed monthly by the Risk & Compliance function, quarterly by the IT Risk Committee, and semi-annually by the Board IT Committee. Each risk carries inherent and residual scoring, a named owner, treatment strategy and target closure date.

## Risk Scoring Matrix
RISK SCORING METHODOLOGY
Likelihood × Impact = Inherent / Residual Score (1–25)
LIKELIHOOD SCALE (1–5)
Score | Rating | Frequency | Description
1 | Rare | <5% in 12 months | Historic — has not occurred at Bank or peer in 5+ years
2 | Unlikely | 5–20% | Could occur but no indication at present
3 | Possible | 20–50% | Has occurred at peers; plausible at Bank
4 | Likely | 50–80% | Has occurred at Bank or is ongoing at peers
5 | Almost Certain | >80% | Ongoing threat; evidence of active attempts
IMPACT SCALE (1–5)
Score | Rating | Financial Impact | Description
1 | Insignificant | <AED 500K | Minor — no customer or regulatory impact
2 | Minor | AED 500K–2M | Some service disruption; internal only
3 | Moderate | AED 2M–10M | Customer-facing disruption; possible regulatory notification
4 | Major | AED 10M–50M | Significant customer harm; regulatory action possible
5 | Severe | >AED 50M | Systemic; loss of license, reputational damage, or customer data breach
RISK APPETITE THRESHOLDS
Score Range | Category | Status | Treatment Required
1–4 | Low |  | Within appetite — monitor only
5–9 | Moderate |  | Within appetite with controls — review quarterly
10–15 | High |  | Outside appetite — formal treatment plan required
16–25 | Extreme |  | Outside appetite — Board notification & immediate remediation

## Risk Register
ENTERPRISE IT RISK REGISTER — AS AT 31-MAR-2026
Risks reviewed by IT Risk Committee on 28-Mar-2026 ¦ Reviewed next: 27-Jun-2026
Risk ID | Risk Title | Category | Description | Owner | Inherent L | Inherent I | Inherent Score | Mitigating Controls | Residual L | Residual I | Residual Score | Treatment | Target Date
R-CY-001 | Ransomware infection across branch network | Cyber | Attacker encrypts branch servers via phishing or compromised RDP exposing 26 branches. | CISO | 4 | 5 | 20 | EDR (CrowdStrike Falcon), weekly patch cycle, air-gapped immutable backups (Rubrik), RDP blocked externally, email sandboxing, quarterly phishing simulations | 2 | 4 | 8 | Reduce | 30-Sep-2026
R-CY-002 | Phishing of privileged staff | Cyber | Targeted spear-phishing of CFO, Treasurer, IT admins to obtain credentials / approve fraudulent transfers. | CISO | 5 | 4 | 20 | MFA on all privileged accounts, email gateway (Proofpoint), monthly phishing sims, out-of-band verification for treasury, PAM (CyberArk) for admin accounts | 3 | 3 | 9 | Reduce | On-going
R-CY-003 | DDoS against Internet Banking platform | Cyber | Volumetric attack degrading availability of IB and mobile banking during peak hours. | CISO | 4 | 3 | 12 | Cloudflare DDoS protection (50 Gbps), dual-ISP (Etisalat/du), WAF rules, CDN, incident runbook tested in Feb-2026 | 2 | 2 | 4 | Reduce | On-going
R-CY-004 | Insider data exfiltration | Cyber | Authorised insider (employee or contractor) exfiltrates customer data to external party. | CISO / HR | 3 | 5 | 15 | DLP (Symantec) on email/web/USB, UEBA via Splunk, data classification enforced, mandatory leave rotation, contractor access via PAM | 2 | 4 | 8 | Reduce | 31-Dec-2026
R-CY-005 | SWIFT payment fraud (BEC) | Cyber | Compromise of SWIFT operator credentials leading to fraudulent outbound messages. | Treasurer / CISO | 3 | 5 | 15 | SWIFT CSP v2024 compliant, segregated SWIFT zone, dual-control, secondary 4-eye approval for >USD 1M, daily reconciliation, CSCF independent assessment (Dec-2025) | 2 | 4 | 8 | Reduce | On-going
R-TC-001 | Core Banking outage (Flexcube) | Technology | Extended CBS downtime beyond RTO due to infrastructure failure, software bug or human error. | CIO | 3 | 5 | 15 | Active-active DC/DR (Dubai ↔ Abu Dhabi), RTO 4h/RPO 15min, quarterly DR drills (last: 18-Mar-2026 PASS), vendor 24x7 support contract | 2 | 4 | 8 | Reduce | On-going
R-TC-002 | Unpatched high/critical vulnerabilities | Technology | Critical vulnerabilities in externally-facing assets remain unpatched past SLA (CBUAE: 30 days). | IT Ops Head | 4 | 4 | 16 | Tenable.io weekly scans, CVSS-based SLA enforcement, monthly Patch Tuesday cycle, emergency patch process, 21 vulns currently open (16 within SLA) | 3 | 3 | 9 | Reduce | On-going
R-TC-003 | Cloud misconfiguration (Azure / AWS) | Technology | Misconfigured cloud workload exposing customer data (open S3 bucket, overly-permissive IAM). | Cloud Architect | 4 | 4 | 16 | CSPM (Wiz) deployed, IaC (Terraform) with policy-as-code, 4-eye review on all cloud changes, CIS benchmarks enforced | 2 | 3 | 6 | Reduce | 30-Jun-2026
R-OP-001 | Third-party / fintech partner breach | Operational | Breach at a fintech/TSP (e.g. payment gateway) exposing Bank customer data or disrupting service. | Vendor Mgmt / CISO | 3 | 4 | 12 | Vendor security assessment (annual), contract clauses (right to audit, breach notify 24h), ISO 27001/PCI-DSS AOC required, PAM for vendor access, 38 vendors on-register | 2 | 3 | 6 | Reduce | On-going
R-OP-002 | Data centre physical incident (fire, flood, power) | Operational | Physical event at primary DC (Deira) disrupts services. | Facilities / CIO | 2 | 5 | 10 | Tier III certified DC, FM-200 suppression, N+1 UPS & generator (72h fuel), secondary DC in Mussafah, annual fire drill | 1 | 4 | 4 | Reduce | On-going
R-OP-003 | Key-person dependency (IT / InfoSec) | Operational | Loss of single subject-matter expert (e.g. Core Banking DBA) disrupts operations. | HR / CIO | 4 | 3 | 12 | Succession plan documented for 12 critical roles, cross-training programme, all runbooks in Confluence, dual-coverage rota | 3 | 2 | 6 | Reduce | 31-Dec-2026
R-CM-001 | Non-compliance with CBUAE reporting (S.14.10.7) | Compliance | Failure to submit cyber incident report within required timelines post-incident. | CISO | 2 | 5 | 10 | Incident Response Plan (v4.2), on-call CISO delegate, 30-min pager response, regulatory template prefilled, Compliance function notification in parallel | 1 | 4 | 4 | Reduce | On-going
R-CM-002 | PCI-DSS v4.0.1 gap — MFA for all admin access | Compliance | Residual gap on PCI Req 8.4.2 / 8.5 (phishing-resistant MFA) for cardholder data environment admins. | CISO / QSA | 3 | 4 | 12 | FIDO2 hardware tokens deployed for CDE admins (29 of 32 covered), remaining 3 on roadmap Q2-2026, compensating control logged with QSA | 2 | 3 | 6 | Reduce | 30-Jun-2026
R-CM-003 | Data Protection Law (UAE PDPL) consent drift | Compliance | Customer marketing consent not captured/refreshed per PDPL for pre-2022 customer base. | DPO / Compliance | 4 | 3 | 12 | Consent re-capture campaign in progress (62% complete), DPIA updated, CRM enhanced to enforce consent at point of contact | 2 | 3 | 6 | Reduce | 31-Dec-2026
R-FR-001 | Internet banking account takeover (ATO) | Fraud | Customer IB credentials phished or SIM-swapped leading to unauthorised transactions. | Fraud / CISO | 4 | 4 | 16 | Mandatory OTP/MFA (SBP IB 2.2.1), device binding, risk-based authentication, transaction monitoring (Featurespace), 30-min cooling period for beneficiary add, SMS alerts | 3 | 3 | 9 | Reduce | On-going
R-FR-002 | Mobile malware on customer device | Fraud | Overlay/banking trojan (e.g. Anubis) on customer Android compromising IB session. | Fraud / CISO | 4 | 3 | 12 | App shielding (Promon SHIELD), jailbreak/root detection, customer awareness campaigns, behavioural analytics on transactions | 3 | 2 | 6 | Reduce | On-going
R-AP-001 | Core Banking release defect | Application | Poorly tested CBS release causes transaction corruption or service outage. | CIO / QA Head | 3 | 4 | 12 | 4-stage SDLC (DEV→SIT→UAT→PROD), mandatory peer review, automated regression, change advisory board, rollback plan required, UAT sign-off by Business | 2 | 3 | 6 | Reduce | On-going
R-AP-002 | Supply chain attack via open-source dependency | Application | Malicious code injected into widely-used library (e.g. log4shell-class). | CISO / DevSecOps | 3 | 4 | 12 | SCA (Snyk) in CI/CD, SBOM maintained, private artifact repository, critical CVE alerting, 72h triage SLA | 2 | 3 | 6 | Reduce | On-going

## Summary Dashboard
RISK REGISTER SUMMARY DASHBOARD
As at 31-Mar-2026
RISKS BY CATEGORY
Category | Count | % of Total | High/Extreme | Mitigation Status
Cyber | 5 | 28% | 0 | All controls operating effectively
Technology | 3 | 17% | 1 | All controls operating effectively
Operational | 3 | 17% | 0 | All controls operating effectively
Compliance | 3 | 17% | 1 | 2 remediation items open
Fraud | 2 | 11% | 0 | All controls operating effectively
Application | 2 | 11% | 0 | All controls operating effectively
RESIDUAL RISK DISTRIBUTION
Risk Level | Count | % of Total | Target State | Action
Low (1-4) | 12 | 67% | Monitor | Quarterly review
Moderate (5-9) | 6 | 33% | Within appetite | Controls maintained
High (10-15) | 0 | 0% | Treat | Remediation plan
Extreme (16-25) | 0 | 0% | Escalate | Board notification
SIGN-OFF
Prepared by | Head of Information Security | 31-Mar-2026 | [Signature] | [Stamp]
Reviewed by | Chief Information Security Officer | 31-Mar-2026 | [Signature] | [Stamp]
Endorsed by | IT Risk Committee | 28-Mar-2026 | [Signature] | [Stamp]
Approved by | Board IT Committee | 15-Apr-2026 | [Signature] | [Stamp]