## Template
Risk ID | Risk Title | Risk Description | Risk Category | COBIT 2019 APO12 Practice Mapping | Business Process / Service Affected | Information Asset / Technology Asset | Asset Owner | Risk Owner | Risk Source / Trigger | Threat / Event Scenario | Vulnerability / Condition | Potential Business Impact | Impact Type | Inherent Likelihood | Inherent Impact | Inherent Risk Rating | Existing Controls | Control Effectiveness | Residual Likelihood | Residual Impact | Residual Risk Rating | Risk Appetite / Tolerance Threshold | Risk Appetite Status | Risk Treatment Option | Treatment Plan / Required Actions | Treatment Owner | Target Completion Date | Treatment Status | Residual Risk Acceptance Required | Risk Acceptance Approver | Risk Acceptance Date | Acceptance Expiry / Review Date | Key Risk Indicator | KRI Threshold | Current KRI Value | Linked Incident / Issue / Audit Finding | Related Policies / Standards | Related Control References | Dependencies / Assumptions | Last Reviewed Date | Next Review Date | Risk Status | Comments / Review Notes
[EXAMPLE: IT-RISK-0001] | [EXAMPLE: Unsupported operating systems on critical servers] | [EXAMPLE: Unsupported server operating systems may expose critical applications to unpatched vulnerabilities, resulting in service disruption or data compromise.] | [EXAMPLE: Infrastructure] | [EXAMPLE: APO12.01; APO12.02; APO12.06] | [EXAMPLE: Customer billing service] | [EXAMPLE: Billing application servers] | [EXAMPLE: Head of Infrastructure] | [EXAMPLE: IT Operations Manager] | [EXAMPLE: Vulnerability assessment] | [EXAMPLE: Exploitation of unpatched OS vulnerability] | [EXAMPLE: Vendor support ended and no security patches are available] | [EXAMPLE: Billing outage, regulatory reporting delay, and potential unauthorised access to customer data] | [EXAMPLE: Operational; Data Confidentiality; Regulatory / Legal] | [EXAMPLE: 4] | [EXAMPLE: 5] | [EXAMPLE: Critical / 20] | [EXAMPLE: Network segmentation CTRL-NET-004; EDR CTRL-END-002; vulnerability scanning CTRL-VM-001] | [EXAMPLE: Partially Effective] | [EXAMPLE: 3] | [EXAMPLE: 5] | [EXAMPLE: High / 15] | [EXAMPLE: Residual risk must not exceed Medium for internet-facing critical systems] | [EXAMPLE: Outside Appetite] | [EXAMPLE: Mitigate] | [EXAMPLE: Migrate servers to supported OS version and decommission unsupported instances] | [EXAMPLE: Infrastructure Platform Lead] | [EXAMPLE: 2026-03-31] | [EXAMPLE: In Progress] | [EXAMPLE: Yes] | [EXAMPLE: CIO] | [EXAMPLE: 2026-01-15] | [EXAMPLE: 2026-04-15] | [EXAMPLE: Number of unsupported critical servers] | [EXAMPLE: 0 unsupported critical servers] | [EXAMPLE: 6 as of 2026-01-10] | [EXAMPLE: AUD-2026-004] | [EXAMPLE: Vulnerability Management Standard; Secure Configuration Standard] | [EXAMPLE: COBIT APO12; CIS Control 7; ISO 27001 A.8.8] | [EXAMPLE: Migration depends on application compatibility testing and approved maintenance window] | [EXAMPLE: 2026-01-15] | [EXAMPLE: 2026-02-15] | [EXAMPLE: Under Treatment] | [EXAMPLE: Risk accepted temporarily pending migration plan completion.]
[EXAMPLE: IT-RISK-0002] | [EXAMPLE: Excessive privileged access in cloud platform] | [EXAMPLE: Over-assigned administrative privileges in the cloud environment may allow accidental or malicious changes, causing data exposure or service disruption.] | [EXAMPLE: Cloud] | [EXAMPLE: APO12.01; APO12.03; APO12.04] | [EXAMPLE: Online sales platform] | [EXAMPLE: Production cloud subscription] | [EXAMPLE: Cloud Service Owner] | [EXAMPLE: Head of Cloud Engineering] | [EXAMPLE: Internal control review] | [EXAMPLE: Misuse or compromise of privileged cloud account] | [EXAMPLE: Privileged roles not reviewed regularly and standing access is assigned] | [EXAMPLE: Unauthorised configuration changes, customer data exposure, and prolonged service outage] | [EXAMPLE: Data Confidentiality; Data Availability; Reputational] | [EXAMPLE: 4] | [EXAMPLE: 4] | [EXAMPLE: High / 16] | [EXAMPLE: MFA CTRL-IAM-001; central logging CTRL-LOG-003] | [EXAMPLE: Partially Effective] | [EXAMPLE: 3] | [EXAMPLE: 4] | [EXAMPLE: High / 12] | [EXAMPLE: Privileged access risks must be Medium or below] | [EXAMPLE: Outside Appetite] | [EXAMPLE: Mitigate] | [EXAMPLE: Implement privileged access management, quarterly access recertification, and just-in-time admin elevation] | [EXAMPLE: Identity and Access Management Lead] | [EXAMPLE: 2026-04-30] | [EXAMPLE: Not Started] | [EXAMPLE: No] | [EXAMPLE: N/A] | [EXAMPLE: N/A] | [EXAMPLE: N/A] | [EXAMPLE: Percentage of privileged accounts recertified within SLA] | [EXAMPLE: 100% recertified every quarter] | [EXAMPLE: 62% as of 2026-01-10] | [EXAMPLE: ISSUE-2026-018] | [EXAMPLE: Access Control Policy; Cloud Security Standard] | [EXAMPLE: COBIT APO12; COBIT DSS05; ISO 27001 A.5.15; CIS Control 6] | [EXAMPLE: Requires integration between cloud IAM and enterprise PAM platform] | [EXAMPLE: 2026-01-10] | [EXAMPLE: 2026-02-10] | [EXAMPLE: Open] | [EXAMPLE: Escalated to Cloud Governance Board due to residual risk outside appetite.]

## Column Guidance
Column | What to enter
Risk ID | Enter a unique identifier for the risk using the organisation's naming convention, e.g. IT-RISK-0001. Do not reuse IDs.
Risk Title | Enter a short, specific title describing the risk scenario in business terms.
Risk Description | Describe the risk clearly as a cause-event-impact statement, explaining what could happen and why it matters.
Risk Category | Select the primary risk category. Allowed values: Cybersecurity, Data Protection, Technology Resilience, Third Party, Cloud, Application, Infrastructure, Identity and Access, Change, Compliance, Project / Transformation, Operational IT, Other.
COBIT 2019 APO12 Practice Mapping | Enter the applicable COBIT 2019 APO12 management practice reference(s). Allowed values include APO12.01, APO12.02, APO12.03, APO12.04, APO12.05, APO12.06; enter multiple values separated by semicolons if needed.
Business Process / Service Affected | Enter the business process, IT service, product, or capability affected by the risk.
Information Asset / Technology Asset | Enter the key information asset, application, infrastructure component, platform, data set, or technology environment affected.
Asset Owner | Enter the accountable owner of the affected asset, using role or named individual according to organisational practice.
Risk Owner | Enter the accountable person or role responsible for managing the risk and ensuring treatment progress.
Risk Source / Trigger | Enter how the risk was identified or what triggered it, e.g. risk assessment, incident, audit finding, regulatory change, project review, supplier assessment, vulnerability assessment.
Threat / Event Scenario | Describe the threat, event, or scenario that could exploit the condition, such as ransomware attack, privileged access misuse, supplier outage, data leakage, or failed change.
Vulnerability / Condition | Describe the weakness, exposure, control gap, or condition that makes the risk possible.
Potential Business Impact | Describe the realistic business consequence if the risk materialises, including operational, financial, regulatory, customer, safety, reputational, or strategic impact.
Impact Type | Select all applicable impact types. Allowed values: Financial, Operational, Regulatory / Legal, Reputational, Customer, Safety, Data Confidentiality, Data Integrity, Data Availability, Strategic; separate multiple values with semicolons.
Inherent Likelihood | Enter the likelihood before considering existing controls. Use the organisation's approved scale, e.g. 1-5 where 1 = Rare and 5 = Almost Certain.
Inherent Impact | Enter the impact before considering existing controls. Use the organisation's approved scale, e.g. 1-5 where 1 = Insignificant and 5 = Severe.
Inherent Risk Rating | Enter the inherent risk score or rating calculated using the organisation's risk matrix, e.g. Likelihood x Impact score and/or Low, Medium, High, Critical.
Existing Controls | List the current controls that reduce the risk, including preventive, detective, and corrective controls. Reference control IDs where available.
Control Effectiveness | Assess how well existing controls operate. Allowed values: Effective, Partially Effective, Ineffective, Not Tested, Unknown.
Residual Likelihood | Enter the likelihood after considering existing controls. Use the organisation's approved scale, e.g. 1-5.
Residual Impact | Enter the impact after considering existing controls. Use the organisation's approved scale, e.g. 1-5.
Residual Risk Rating | Enter the residual risk score or rating calculated using the organisation's risk matrix, e.g. Likelihood x Impact score and/or Low, Medium, High, Critical.
Risk Appetite / Tolerance Threshold | Enter the relevant approved appetite or tolerance threshold for this risk type, such as maximum acceptable residual rating, downtime limit, loss threshold, or compliance tolerance.
Risk Appetite Status | State whether residual risk is within tolerance. Allowed values: Within Appetite, Outside Appetite, Not Defined.
Risk Treatment Option | Select the approved treatment decision. Allowed values: Accept, Mitigate, Transfer / Share, Avoid, Monitor.
Treatment Plan / Required Actions | For risks not simply accepted, describe the specific action(s), control improvements, remediation activities, or projects required to reach the target risk level.
Treatment Owner | Enter the person or role accountable for delivering the treatment actions.
Target Completion Date | Enter the planned completion date for treatment actions in YYYY-MM-DD format.
Treatment Status | Enter the current implementation status. Allowed values: Not Started, In Progress, Completed, Deferred, Overdue, Cancelled.
Residual Risk Acceptance Required | State whether formal acceptance is required because residual risk remains outside appetite or exceeds approval thresholds. Allowed values: Yes, No.
Risk Acceptance Approver | If acceptance is required, enter the authorised approver role or name in line with the risk acceptance authority matrix; otherwise enter N/A.
Risk Acceptance Date | If accepted, enter the approval date in YYYY-MM-DD format; otherwise enter N/A.
Acceptance Expiry / Review Date | If accepted, enter the date by which the acceptance must be reviewed or renewed in YYYY-MM-DD format; otherwise enter N/A.
Key Risk Indicator | Enter the measurable indicator used to monitor this risk, e.g. number of critical vulnerabilities older than SLA, phishing failure rate, failed backup percentage.
KRI Threshold | Enter the agreed threshold or trigger level for escalation, including unit of measure, e.g. >10 critical vulnerabilities older than 30 days.
Current KRI Value | Enter the latest measured KRI value and measurement date, e.g. 7 as of YYYY-MM-DD.
Linked Incident / Issue / Audit Finding | Enter references to related incidents, problems, issues, audit findings, compliance findings, or vulnerability records; enter N/A if none.
Related Policies / Standards | Enter applicable internal policies, standards, or procedures relevant to this risk, such as Information Security Policy or Backup Standard.
Related Control References | Enter relevant control references from internal control libraries, COBIT objectives, ISO 27001, NIST, CIS, or other frameworks used by the organisation.
Dependencies / Assumptions | Record key dependencies or assumptions affecting the risk assessment or treatment, such as supplier delivery, budget approval, architecture change, or resource availability.
Last Reviewed Date | Enter the date this risk entry was last formally reviewed in YYYY-MM-DD format.
Next Review Date | Enter the next scheduled review date in YYYY-MM-DD format, based on risk rating and organisational review frequency.
Risk Status | Enter the lifecycle status of the risk. Allowed values: Open, Under Treatment, Accepted, Monitored, Closed, Escalated.
Comments / Review Notes | Enter concise notes from the latest review, including decisions, changes in rating, escalation outcomes, or reasons for closure.

## Notes
Maintenance
The IT Risk Register template is owned by the IT Risk Manager or equivalent technology risk function, with risk entries maintained by assigned risk owners and reviewed at least monthly for high and critical risks and quarterly for all other risks. Source data should be drawn from the enterprise GRC platform or risk management system, supported by inputs from CMDB/asset inventory, vulnerability management tools, incident management, audit issue tracking, supplier risk assessments, and project governance records.