## Risk Register
INTERNAL RISK REGISTER
Enterprise Risk Management — Confidential
Total Risks |  | Critical / High |  | Medium |  | Low |  | Open |  | In Progress |  | Closed |  | Avg Risk Score
50 |  | 29 |  | 21 |  | 0 |  | 26 |  | 20 |  | 4 |  | 11.16
Risk ID | Risk Category | Sub-Category | Risk Title | Risk Description | Risk Owner | Department | Likelihood (1–5) | Impact (1–5) | Risk Score | Risk Level | Inherent Risk | Control Description | Status | Target Date | Residual Risk | Last Reviewed | Notes
RSK-001 | Operational | Process Failure | Critical Process Breakdown | Key operational processes lack documented procedures and backups, risking service disruption | COO | Operations | 4 | 4 | 16 | High | High | SOPs documented; quarterly process audits | Open | 2026-03-31 | Medium | 2026-01-15 | Priority remediation item
RSK-002 | Operational | Human Error | Data Entry Errors | Manual data entry processes result in inaccurate records impacting business decisions | Ops Manager | Operations | 4 | 3 | 12 | High | High | Input validation controls; dual-entry checks | In Progress | 2026-02-28 | Medium | 2026-01-15 | Automation in progress
RSK-003 | Operational | Vendor Management | Third-Party Vendor Failure | Reliance on single-source vendors creates operational continuity risk | Procurement Dir | Procurement | 3 | 4 | 12 | High | High | Vendor diversification; SLA enforcement | Open | 2026-06-30 | Medium | 2026-01-15 | Vendor audit scheduled Q2
RSK-004 | Operational | Capacity Planning | Resource Constraints | Insufficient staffing during peak periods leads to service degradation | HR Director | Human Resources | 3 | 3 | 9 | Medium | Medium | Seasonal hiring plan; cross-training | In Progress | 2026-04-15 | Medium | 2026-01-15 | Headcount review underway
RSK-005 | Operational | Change Management | Uncontrolled Change Implementation | System or process changes deployed without adequate testing or rollback plans | IT Director | IT | 4 | 4 | 16 | High | High | Change advisory board; staged rollouts | Open | 2026-02-15 | Medium | 2026-01-15 | CAB policy being drafted
RSK-006 | Financial | Budget Overrun | Project Cost Escalation | Projects consistently exceed approved budgets due to poor estimation and scope creep | CFO | Finance | 4 | 3 | 12 | High | High | Stage-gate approvals; budget variance reporting | In Progress | 2026-03-01 | Medium | 2026-01-15 | Monthly budget reviews instituted
RSK-007 | Financial | Fraud | Internal Fraud & Misappropriation | Inadequate segregation of duties creates opportunity for internal financial fraud | CFO | Finance | 2 | 5 | 10 | High | High | Dual approval workflows; internal audit program | Open | 2026-01-31 | Medium | 2026-01-15 | Segregation of duties review due
RSK-008 | Financial | Liquidity | Cash Flow Shortfall | Unexpected revenue dips or delayed receivables could impair near-term liquidity | Treasurer | Finance | 3 | 4 | 12 | High | High | Rolling 13-week cash forecast; credit facility | Open | 2026-03-15 | Medium | 2026-01-15 | Cash model updated monthly
RSK-009 | Financial | FX Exposure | Foreign Currency Risk | International transactions expose the company to adverse currency fluctuations | CFO | Finance | 3 | 3 | 9 | Medium | Medium | FX hedging policy; natural hedging | Closed | 2025-12-31 | Low | 2026-01-15 | Hedging program active
RSK-010 | Financial | Tax Compliance | Transfer Pricing Non-Compliance | Intercompany transactions may not meet arm's-length transfer pricing standards | Tax Director | Finance | 2 | 4 | 8 | Medium | Medium | Annual TP study; Big 4 advisor review | In Progress | 2026-06-30 | Medium | 2026-01-15 | TP documentation update in progress
RSK-011 | Technology | Cybersecurity | Ransomware Attack | Phishing or unpatched systems could allow ransomware to encrypt critical data | CISO | IT Security | 4 | 5 | 20 | Critical | Critical | EDR tooling; immutable backups; user training | Open | 2026-01-31 | Medium | 2026-01-15 | Tabletop exercise Q1 2026
RSK-012 | Technology | Cybersecurity | Insider Threat | Privileged users may intentionally or accidentally exfiltrate sensitive data | CISO | IT Security | 3 | 4 | 12 | High | High | UEBA monitoring; least-privilege access | In Progress | 2026-03-01 | Medium | 2026-01-15 | DLP deployment ongoing
RSK-013 | Technology | Infrastructure | System Downtime | Critical systems lack adequate redundancy causing extended outages | IT Director | IT | 3 | 4 | 12 | High | High | HA architecture; RTO/RPO targets defined | In Progress | 2026-04-30 | Medium | 2026-01-15 | DR site upgrade planned
RSK-014 | Technology | Data Management | Data Loss / Corruption | Inadequate backup and recovery procedures risk permanent data loss | IT Director | IT | 3 | 5 | 15 | High | High | Daily backups; annual DR test | Open | 2026-02-28 | Medium | 2026-01-15 | DR test overdue
RSK-015 | Technology | Software Development | Vulnerable Code in Production | Insecure coding practices introduce exploitable vulnerabilities in applications | CTO | Engineering | 4 | 4 | 16 | High | High | SAST/DAST scanning; secure SDLC | In Progress | 2026-03-31 | Medium | 2026-01-15 | DevSecOps pipeline in build
RSK-016 | Technology | Access Control | Orphaned Privileged Accounts | Terminated employees retain active system access beyond offboarding | IT Director | IT | 3 | 4 | 12 | High | High | Automated de-provisioning; quarterly access review | Open | 2026-01-15 | Medium | 2026-01-15 | Access recertification campaign needed
RSK-017 | Technology | Cloud | Cloud Misconfiguration | Misconfigured cloud resources expose sensitive data to public internet | Cloud Architect | IT | 4 | 4 | 16 | High | High | CSPM tooling; cloud security baseline | In Progress | 2026-02-28 | Medium | 2026-01-15 | CSPM tool deployed, remediation ongoing
RSK-018 | Technology | AI/ML | Biased AI Model Outputs | Machine learning models produce biased or inaccurate recommendations affecting decisions | Data Science Lead | Analytics | 3 | 3 | 9 | Medium | Medium | Model validation; bias testing; human review | Open | 2026-06-30 | Medium | 2026-01-15 | AI governance policy in draft
RSK-019 | Compliance | Regulatory | Data Privacy Regulation Breach | Non-compliance with GDPR, CCPA or local privacy laws results in regulatory fines | DPO | Legal | 3 | 5 | 15 | High | High | Privacy impact assessments; consent management | In Progress | 2026-03-31 | Medium | 2026-01-15 | DPIA backlog being cleared
RSK-020 | Compliance | Regulatory | Employment Law Violations | HR policies not aligned with evolving employment regulations in operating jurisdictions | CHRO | Human Resources | 2 | 4 | 8 | Medium | Medium | Annual policy review; employment counsel | Open | 2026-05-31 | Medium | 2026-01-15 | Multi-jurisdiction review needed
RSK-021 | Compliance | Contractual | Contract Non-Performance | Failure to meet contractual SLAs triggers financial penalties and reputational damage | Legal Counsel | Legal | 3 | 3 | 9 | Medium | Medium | SLA monitoring dashboards; escalation protocols | In Progress | 2026-02-28 | Medium | 2026-01-15 | SLA dashboard in development
RSK-022 | Compliance | Anti-Bribery | FCPA / Bribery Act Exposure | Operations in higher-risk jurisdictions create anti-bribery compliance obligations | CLO | Legal | 2 | 4 | 8 | Medium | Medium | ABAC policy; gift and hospitality register | Open | 2026-04-30 | Medium | 2026-01-15 | Training completion at 60%
RSK-023 | Compliance | Licensing | Software Licensing Non-Compliance | Untracked software usage may exceed license entitlements exposing company to audits | IT Director | IT | 3 | 3 | 9 | Medium | Medium | SAM tooling; annual software audit | In Progress | 2026-03-31 | Medium | 2026-01-15 | SAM tool implementation in progress
RSK-024 | Strategic | Market | Competitive Disruption | New market entrants or disruptive technologies erode company's competitive position | CEO | Executive | 3 | 4 | 12 | High | High | Competitive intelligence program; product roadmap reviews | Open | 2026-06-30 | Medium | 2026-01-15 | Quarterly strategy reviews
RSK-025 | Strategic | M&A | Post-Merger Integration Failure | Acquisitions fail to deliver expected synergies due to poor integration planning | CEO | Executive | 3 | 4 | 12 | High | High | 100-day integration playbook; integration PMO | Open | 2026-09-30 | Medium | 2026-01-15 | Playbook drafted for next acquisition
RSK-026 | Strategic | Innovation | Failure to Innovate | Slow product development cycle causes loss of market share to agile competitors | CTO | Product | 4 | 3 | 12 | High | High | Innovation sprints; R&D investment targets | In Progress | 2026-06-30 | Medium | 2026-01-15 | Product velocity metrics being tracked
RSK-027 | Strategic | Concentration | Customer Concentration Risk | Over-reliance on top 3 customers creates significant revenue concentration risk | CRO | Sales | 4 | 4 | 16 | High | High | Customer diversification strategy; retention programs | Open | 2026-09-30 | Medium | 2026-01-15 | New vertical sales motion launched
RSK-028 | Strategic | Reputational | Brand & Reputation Damage | Negative media coverage or social media incidents erode brand trust and customer loyalty | CMO | Marketing | 3 | 4 | 12 | High | High | PR crisis plan; social media monitoring | Open | 2026-03-31 | Medium | 2026-01-15 | Crisis comms playbook in review
RSK-029 | People | Talent | Key Person Dependency | Critical institutional knowledge concentrated in a few individuals creates succession risk | CHRO | Human Resources | 4 | 4 | 16 | High | High | Succession planning; knowledge documentation | In Progress | 2026-06-30 | Medium | 2026-01-15 | Succession plans for top 20 roles
RSK-030 | People | Talent | High Attrition / Talent Drain | Elevated employee turnover disrupts operations and increases recruitment costs | CHRO | Human Resources | 4 | 3 | 12 | High | High | Stay interviews; compensation benchmarking | Open | 2026-03-31 | Medium | 2026-01-15 | Engagement survey results pending
RSK-031 | People | Culture | Workplace Harassment | Inadequate reporting mechanisms allow harassment or discrimination to go unaddressed | CHRO | Human Resources | 2 | 4 | 8 | Medium | Medium | Anonymous hotline; mandatory training | In Progress | 2026-04-30 | Medium | 2026-01-15 | Training completion at 75%
RSK-032 | People | Health & Safety | Workplace Injury | Inadequate safety protocols expose employees to physical injury risks | Facilities Mgr | Facilities | 2 | 4 | 8 | Medium | Medium | Safety audits; incident reporting system | Closed | 2025-09-30 | Low | 2026-01-15 | Annual audit completed
RSK-033 | People | Remote Work | Remote Work Security Gaps | Remote employees access sensitive systems from unsecured home networks | CISO | IT Security | 4 | 3 | 12 | High | High | VPN mandate; endpoint management; training | Closed | 2025-12-31 | Low | 2026-01-15 | Zero Trust rollout complete
RSK-034 | Environmental | Climate | Physical Climate Risk | Extreme weather events disrupt operations at key facilities | Facilities Mgr | Facilities | 3 | 3 | 9 | Medium | Medium | Business continuity plans; facility assessments | Open | 2026-12-31 | Medium | 2026-01-15 | Climate risk assessment initiated
RSK-035 | Environmental | ESG | ESG Reporting Non-Compliance | Inability to produce accurate ESG metrics leads to investor and regulatory scrutiny | CFO | Finance | 3 | 3 | 9 | Medium | Medium | ESG data collection framework; third-party audit | In Progress | 2026-06-30 | Medium | 2026-01-15 | ESG framework being implemented
RSK-036 | Environmental | Waste | Improper Waste Disposal | Non-compliant disposal of operational waste violates environmental regulations | Facilities Mgr | Facilities | 2 | 3 | 6 | Medium | Medium | Waste management policy; approved vendor use | Closed | 2025-11-30 | Low | 2026-01-15 | Vendor contracts renewed
RSK-037 | Legal | Litigation | Material Litigation Exposure | Pending or threatened lawsuits create financial liability and management distraction | CLO | Legal | 3 | 4 | 12 | High | High | Litigation reserve; outside counsel management | In Progress | 2026-06-30 | Medium | 2026-01-15 | 3 open matters being managed
RSK-038 | Legal | IP | Intellectual Property Infringement | Competitors or employees misappropriate proprietary IP or trade secrets | CLO | Legal | 2 | 4 | 8 | Medium | Medium | IP inventory; NDA enforcement; monitoring | Open | 2026-06-30 | Medium | 2026-01-15 | IP audit in scope for 2026
RSK-039 | Legal | Product Liability | Product Recall Risk | Product defects result in recalls, regulatory action, or personal injury claims | CTO | Engineering | 2 | 5 | 10 | High | High | Quality management system; product testing | Open | 2026-06-30 | Medium | 2026-01-15 | Quality gate review scheduled
RSK-040 | Legal | Privacy | Biometric Data Misuse | Collection of biometric data without compliant consent frameworks creates legal exposure | DPO | Legal | 2 | 4 | 8 | Medium | Medium | Consent management; data minimization policy | Open | 2026-03-31 | Medium | 2026-01-15 | Policy drafted, legal review pending
RSK-041 | Supply Chain | Disruption | Raw Material Shortages | Geopolitical or logistical disruptions create critical raw material supply gaps | COO | Operations | 3 | 4 | 12 | High | High | Dual sourcing; safety stock targets | In Progress | 2026-04-30 | Medium | 2026-01-15 | Safety stock levels under review
RSK-042 | Supply Chain | Logistics | Distribution Network Failure | Reliance on single logistics partners creates fulfillment risk during peak periods | COO | Operations | 3 | 3 | 9 | Medium | Medium | Multi-carrier strategy; 3PL agreements | Open | 2026-06-30 | Medium | 2026-01-15 | 3PL RFP in progress
RSK-043 | Supply Chain | Geopolitical | Tariff & Trade Policy Changes | Shifting trade policies increase input costs and disrupt cross-border supply chains | CFO | Finance | 3 | 3 | 9 | Medium | Medium | Tariff monitoring; pricing flexibility provisions | Open | 2026-12-31 | Medium | 2026-01-15 | Trade counsel engaged
RSK-044 | Operational | Business Continuity | Pandemic / Mass Absence | Large-scale employee absence disrupts operations with no tested BCP in place | COO | Operations | 2 | 4 | 8 | Medium | Medium | BCP framework; cross-training; remote capability | In Progress | 2026-06-30 | Medium | 2026-01-15 | BCP plan refresh underway
RSK-045 | Technology | IoT / OT | OT/IoT Device Compromise | Unmanaged IoT and OT devices provide entry points into corporate networks | CISO | IT Security | 3 | 4 | 12 | High | High | Asset inventory; network segmentation; firmware patching | Open | 2026-03-31 | Medium | 2026-01-15 | OT asset discovery underway
RSK-046 | Financial | Insurance | Underinsurance Exposure | Existing insurance policies fail to adequately cover emerging risk categories | CFO | Finance | 2 | 4 | 8 | Medium | Medium | Annual insurance gap analysis; broker review | Open | 2026-04-30 | Medium | 2026-01-15 | Broker review scheduled Q2
RSK-047 | Compliance | Sanctions | Sanctions Screening Gaps | Customers or transactions not screened against current sanctions lists | CLO | Legal | 2 | 5 | 10 | High | High | Automated sanctions screening; regular list updates | In Progress | 2026-02-28 | Medium | 2026-01-15 | Screening tool upgrade in progress
RSK-048 | Strategic | Partnership | Strategic Alliance Failure | Key partnerships or joint ventures fail to deliver expected strategic value | CEO | Executive | 2 | 3 | 6 | Medium | Medium | Partnership governance; KPI-driven reviews | Open | 2026-09-30 | Medium | 2026-01-15 | Partnership review cadence established
RSK-049 | People | Diversity & Inclusion | DEI Commitment Gaps | Failure to meet stated DEI targets damages employer brand and regulatory standing | CHRO | Human Resources | 3 | 3 | 9 | Medium | Medium | DEI KPIs; pay equity audit; ERG support | In Progress | 2026-06-30 | Medium | 2026-01-15 | Pay equity analysis underway
RSK-050 | Technology | API Security | Unsecured API Integrations | Third-party API integrations lack authentication controls exposing sensitive data | CTO | Engineering | 4 | 4 | 16 | High | High | API gateway; OAuth2 enforcement; rate limiting | Open | 2026-03-31 | Medium | 2026-01-15 | API inventory being built
RSK-051 | Operational | Facilities | Critical Facilities Failure | HVAC, power, or physical security failures at key sites disrupt operations | Facilities Mgr | Facilities | 2 | 4 | 8 | Medium | Medium | Preventive maintenance schedule; backup generators | Closed | 2025-10-31 | Low | 2026-01-15 | UPS and generators tested

## Risk Matrix
RISK HEAT MAP — LIKELIHOOD vs IMPACT
Scores = Likelihood × Impact ¦ Max Score = 25
| Impact 1 Negligible | Impact 2 Minor | Impact 3 Moderate | Impact 4 Major | Impact 5 Critical
Likelihood 5 Almost Certain | 5 | 10 | 15 | 20 | 25
Likelihood 4 Likely | 4 | 8 | 12 | 16 | 20
Likelihood 3 Possible | 3 | 6 | 9 | 12 | 15
Likelihood 2 Unlikely | 2 | 4 | 6 | 8 | 10
Likelihood 1 Rare | 1 | 2 | 3 | 4 | 5
CRITICAL / HIGH (Score 15–25)
MEDIUM (Score 8–12)
LOW (Score 1–6)

## Scoring Guide
RISK SCORING GUIDE
LIKELIHOOD SCALE
1 – Rare |  | Event unlikely to occur; < once every 5 years | < 5%
2 – Unlikely |  | Event could occur but not expected; 1–3 years | 5–25%
3 – Possible |  | Event may occur in some circumstances; 1–2 years | 26–50%
4 – Likely |  | Event will probably occur in most circumstances; < 1 year | 51–75%
5 – Almost Certain |  | Event expected to occur in most circumstances; within months | 76–100%
IMPACT SCALE
1 – Negligible |  | Minimal impact; easily absorbed; no disruption to objectives
2 – Minor |  | Minor impact; short-term disruption; < $10K financial loss
3 – Moderate |  | Moderate impact; recoverable within weeks; $10K–$100K loss
4 – Major |  | Significant impact; recovery may take months; $100K–$1M loss
5 – Critical |  | Catastrophic impact; threatens viability; > $1M loss
RISK RATING MATRIX
Critical | 20–25 | Immediate executive action required; board notification
High | 15–19 | Senior management action; formal risk treatment plan
Medium | 8–12 | Management responsibility; mitigation plan required
Low | 1–6 | Routine monitoring; manage through standard procedures
RISK CATEGORIES
Operational |  | Process failures, vendor issues, human error, capacity
Financial |  | Fraud, budget overrun, liquidity, FX, tax
Technology |  | Cybersecurity, infrastructure, cloud, AI/ML, APIs
Compliance |  | Regulatory, contractual, anti-bribery, licensing
Strategic |  | Market, M&A, innovation, concentration, reputation
People |  | Talent, culture, H&S, remote work, DEI
Environmental |  | Climate, ESG reporting, waste management
Legal |  | Litigation, IP, product liability, privacy
Supply Chain |  | Disruption, logistics, geopolitical trade risk

## Dashboard
RISK MANAGEMENT DASHBOARD
Summary view — linked to Risk Register
Total Risks |  | Critical | High | Medium
50 |  | 1 | 28 | 21
Open Risks |  | In Progress | Closed | Avg Score
26 |  | 20 | 4 | 11.16
RISKS BY CATEGORY
Operational | 6 | 12%
Financial | 6 | 12%
Technology | 10 | 20%
Compliance | 6 | 12%
Strategic | 6 | 12%
People | 6 | 12%
Environmental | 3 | 6%
Legal | 4 | 8%
Supply Chain | 3 | 6%